## Bid Project Analysis _Feedback
After Bid Analysis | Date:
Strengths, Weaknesses, Opportunities and Challenges |  |  |  | Project Review:
Estimating Process | Team Meeting Evaluation | Overall Project Rate and Yes/No | Review Questions | General Notes
Was the bid Expectation Timeline Realistic and did Business Development present the proper complexity of the project properly |  |  | Yes or No. If no, Describe Issue/Reason
Did we write scopes before subs proposals? |  |  | 15 days or more = Yes Less than 15 days = No
Did we ensure 3 bids per major trades? |  |  | Yes or No. If "No" refer to weaknesses
Was the ITB sent with reasonable time for subs bidding? |  |  | Yes or No. If "No" refer to weaknesses
Were all Bids saved and submitted properly to the project files? |  |  | Yes or No. If "No" refer to weaknesses
Were Subs communicated with various times via email and phone to reach our goals and communication for RFI's |  |  | Yes or No. If "No" refer to weaknesses
Did we vet all the proposals received? Compass Qualified? |  |  | Yes or No. If "No" refer to weaknesses
Did we ensure a reasonable spread between bidders? |  |  | 5% or less = Yes More than 5% = No
Were prices per SF in correspondence with historical data? If not, please update historical data |  |  | Yes or No. If "No" refer to challenges
Were VE options offered? |  |  | Yes or No. If "No" refer to weaknesses
Were all deliverables ready on time and following the most updated templates? |  |  | Yes or No. If "No" refer to challenges
Was the Estimate 90% ready for Resubmission Review? |  |  | Yes or No. If "No" refer to weaknesses
Did we meet the client's deadline? |  |  | Yes or No. If "No" refer to weaknesses
Strengths
What were your advantages within the project?
What assisted you to provide the best project turnout?
Weaknesses
Where in the project were recourses lacking? |  |  | Yes or No. If "No" refer to weaknesses
What area can you improve to assist this project or in a future one?
What area of the project were most challenging for you? The Team?
What scope elements were missed? Or the most problematic?
Opportunities to Improve (List below are Suggestions Only to Discuses) | Open Discussion
What did I learn from this Bid/Project?
If you rated your Strength less than an 8 above where do you feel you can improve and what steps do you need to take?
Are there any suggestions to update our SOP's or to better our processes?
The Strengths you identified above can you put together a plan to share with the "team"?
What area did you see a higher trend in Price/Product creating a higher than usual Bid?
Challenges Found (List below are suggestions only to discuss) | Open Discussion
Were there any obstacles found within the project? Availability of Subs, Location, Team, Etc. | DISCUSS KEEPING VA ITEMS CONFIDENTIAL IN HARD BID SCENARIO
Was there a challenge of a Scope or Knowledge Base of Project?
Were there any Challenges with Communication with anyone within the Project?
Did you find a Price/Product that significantly changed the or increased the Bid causing additional adjustments?
What is an area where you feel you need to focus on learning before or during your next Bid/Project
General Notes/Details and Information
|  | 0 | Notes about Percentage:
Project Summery and Request for Changes to SOP to Estimating Team:
Employees in Project: