## 2026 Project Safety %
| Week of 2/13/2026 | Week of 2/20/2026 | Week of 2/27/2026 | Week of 3/2/2026 | Week of 3/13/2026 | Week of 3/20/2026 | Week of 3/27/26 | Week of 4/3/2026 | Week of 4/10/2026 | Week Ending 4/17/26
Perla |  |  | 84.7%
Overall housekeeping must be maintained, extension cords must be inspected and maintained, site security must be checked (back gate was found open) - all discussed with lead super.
Hanging Moss | 93.8% |  | 90% |  | 94.3% |  | 95.2% |  |  | 90.2%
| Cut off saw is being used withour a facesheild, corrective actions were taken. Damaged extension ladder was removed from site. Drain pipes were secured to prevent displacement. Seatbelt were enforced on heavy equiment. Unattended excavations were secured. |  | Employees were reminded to wear hardhats while on site. Machine operators were instructed to wear seat belts while operation equipment. Excavation safety was addressed - ladders, sloping, and trenchbox use. Safety standown conducted wit Dirthand to address concerns. |  | Exposed storm drains must remain closed until work is continued/ complete. Alumium ladders must be removed from site. Machine operators were reminded to wear seatbelts. |  | SCS employee was advised to wear hardhat at all times. Dirt Hand was advised, any exposed manholes are to remain closed/covered until work is continued or completed. SCS forklift operator must wear seat belt at all times. Corrective action was taken. Dirt Hand has has improved greatly with excavation safety |  | One aluminum ladder was disposed of during our walkthrough. The jobsite is clean and organized. An AED was ordered for the jobsite trailer. | Don King is to clean up/Remove nails facing upward on wooden 2x4. Don King, KNR Electric, & Empire employees were advised to wear hardhat at all times. Dirt Hand & Empire employee was observed using a grinder and cut off saw with no face shield. Empire employee was observed using a grinder with no guard. Corrective actions taken. Dirt Hand was advised to remove anextension ladder that has been previoulsy reported damaged. SCS employee was observed using an Aframe ladder closed. Corrective actions taken.
Caretta | 95.5% | 92.2% + 93.3% | 91.1% | 89% + 86.8% | 85.7% | 91.4% + 80.3% | 85.6% + 88.9% | 86.3% | 94.4% | 87.5%
| OSHA 300A and Emergency Contact lists missing. Alf bringing to site this week. Pate was observed using a chop saw without a facesheild. Building A stairwell railings need repair. | Tuesday- Fencing was secured around the perimeter of the jobsite, building B housekeeping needs attention, Drywall crew in building C missing hardhats, Tile crew was observed using a grinder without a guard (correction made), Building A stairwell rails were repaired, Dorado Stucco employee was removed permanetly due to repeated safety offences, Power design improperly using ladders Friday - Improper ladder use was noted throughout the jobsite. Corrections were made. | Hardhats were not worn by multiple subcontractors. Saws and grinders were in use throughout the jobsite without proper PPE. Corrections made. Scaffolding Tags were missing. An employee was seeing standing on the top rung of a ladder. Machine operators were reminded to wear seatbelts. Sweeping compound was provided after employees were seen sweeping in bldg B. | Monday - Subcontractors are not signing in daily. All subcontractors have at least one employee seen without a hardhat. Multiple employees on site were observed using handheld saws, drills, and cut off saws without eye, face or respiratory protection where needed. Safeguards where on in place on grinders. An aluminum ladder was removed from bldg C lvl 4. Scaffolding on E elevation of bldg C was missing inspection tag and access ladder. Machine operators were directed to use seatbelts. A control access zone must be set up in the plaza under the welding of the steal beams. Wednesday - Hardhat usage throught site was still not in compliance. Dorado drywall and framing employees have been advised multiple times to avoid using non-commercial graded extension cords and how unorganized cords in the hall pose a trip hazard. A follow up meeting with there supervisor will be scheduled along with a safetystandown. AEDC was advised to provide a flagger to prevent endangering the public road when entering and exiting the site. Multiple employees were observed on bldg D lvl 5 balcony with no fall protection and a Plaster working off a scaffold near a leading edge. Corrective actions were made | Monday - Immediate attention to housekeeping required. Hard hats missing from multiple subs on site. Tile crew was reminded to keep grinder guard on at all times. Crown employee was on Bld D balcony with a harness and rope lifeline unattached. Employee utilizing top step of a ladder was advised to get a taller ladder. Damaged extension cords were removed from service. A fire extinguisher must be abailable near work area due to live sparks when welding. Metal framing is being stacked vertically in bldgs A and B. Material is being left in stairwells. Machine operators seen without seatbelts. Due to the amount of deliveries arriving and vehicles entering site from Donlad Ross, a flagger must be present at all times to control/direct traffic. | Monday- Great improvement in housekeeping across project. Hardhats continue to not be worn by multiple subcontractors. A plumber was sent home after repeatedly being asked to don his hardhat. Although railings are installed on balconies, fall protection must still be worn until glass is installed. Access ladder and inspection tag is needed on scaffolding on the east side of Bldg C. Temp electrical box in bldg D lvl 2 must be secured. Due to the amount of deliveries arriving and vehicles entering site from Donlad Ross, a flagger must be present at all times to control/direct traffic. Wednesday - Power Design, Tile crew, Talbot, Everlast have employees with no hardhats equipped. Tile crew must wear eye protection when cutting tile.Tile crew was observed cutting with no dust mask. Everlast employee was on stilts using sneakers, he did not bring boots on site.Christian Glass working on balconies with railings pending glass, must wear fall protection. Fall Protection is used on all Aerial lifts. Tile Crew has two aluminum ladders. They were advised to use Fiberglass ladders moving forward. Talbot Painter was on a baker scaffold with wheels unlocked. Corrective actions were made. Everlast & Tile crew have extension cords not rated for commercial use. Everlast & Tile crew have several patches on their extension cords.Great job with LOTO and signage. Everlast & tile crew have extension cords unrated for commercial use. American & Everlast forklift and heavy machinery operators were reminded to don seatbelts. American, exposed excavations must be protected from other trades at all times. American employees were observed in a trench box with no ladder. Due to the amount of deliveries arriving and vehicles entering/exiting, A flagger must be present at all times to control and direct traffic. | Tuesday- WBCS & Everlast have employees with no hardhats equipped. Corrective action taken. Tile crew must wear eye protection when cutting tile. (2nd Offense)Tile crew has multiple grinders with no guards. BLDG A the stair well needs attention to wooden barriers. LVL 1-5. Stucco crew working on balconies with railings pending glass, must wear fall protection. Tile Crew has two aluminum ladders. They were advised to use Fiberglass ladders moving forward. (2nd offense) JWC was advised on how to use a GFCI properly. Tile crew have extension cords not rated for commercial use. Oceana was charging a Vac Glass Lifter with a damaged extension cord (no ground prong) in BLDG C. Power Design need to tighten up low hanging temp lights. Pate has a forklift that was reported for not having a back up alarm. Thursday- Pate was advised to use rebar caps on areas left in progress. Immediate corrective action taken. verlast & WBCS employees were advised to wear hardhat at all times. Tile crew has multiple grinders with no guards. (Repeated Offense) Coastal Metal was reported for leaving work areas unprotected. Corrective actions taken. Tile crew was reported for multiple extension cords unrated for commercial work. They were removed from service. Everlast forklift operator was reminded to use seatbelt. Pate Forklift was repaired for damaged back up alarm. Good Job. Pate was advised to clear a path between Building A and their excavation site. Corrective action taken. American pipe crew was reminded to use a ladder before entering a tench/excavation. Immediate corrective action taken. | Tuesday - Everlast employees were advised to wear hardhat at all times. Power Design employees using a chipping hammer must wear safety glasses at all times. Jack Walsh employee was advised to use gloves when using a hole saw. Coastal Metal was reported for leaving work areas unprotected. Corrective actions taken. A Christian Glass employees were advised safety straps are to be used for one employee at a time. Interior wood ceiling trim team was advised to not use top step on a ladder. Corrective actions made. Coastal Metal was advised baker scaffold must be fully assembled before use. Wheels were missing. Jack Walsh employee was reported for multiple extension cords unrated for commercial work. They were removed from service. Materials & equipment is beginning to crowd the first floor or Bldg A. Subs are to organize and keep travel paths clear. An unoccupied Duct Jack was reported for having non compliant configuration. Item was removed from further use. Everlast forklift operator was reminded to use seatbelt. Building A needs attention on level 1. All subs must organize materials and equipment. | Tuesday - Major housekeeping is in progress and clean up crews are working in all buildings. Crown employees were advised sneakers are not allowed on site. Boots must be worn at all times. A damaged ladder was identified and removed from service. American was in a trench box with no ladder. Corrective actions made. A safety standdown was held with all subcontractors to communicate specific work task and safety expectations. Housekeeping was addressed to remove debris from the buildings and prevent trip hazards. | Dorado & Jack Walsh employees were advised to equip hard hat at all times. Jack Walsh employees are not using safety glasses when cutting. Jack Walsh employees are cutting tile with no respiratory protection. Jack Walsh employees are using grinders with no guards. Talbot Painting is doing a great job with ladder use. PDI employee was observed using an A frame ladder closed. Corrective actions made. Dorado employee was advised the top step reduces stability. Corrective actions made. Coastal Metal was observed using a scaffold missing a brace. Coastal Metal is not using locking the wheels. Corrective actions made. Temp power boxes need to be set up on a stand or against the wall. Building D. Coastal Metal Duct Jack was reported for having non compliant configuration. Repeated offense. Jack Walsh employee was observed stopping a grinder from spinning with his boots! Reported to HB superintendent.
YMCA | 98.7% | 100% | 95.3% | 100% | 100% | 96% + 100% | 100% | 100% +100% | 98.3% + 100% | 100%
| Guard missing on steel workers grinder. Grinder was removed from service. |  | Blockmason using saw without face protection, Welder was reminded to have designated fire extinguisher, plastic gas can was removed from site, and forklift operator was reminded to wear seatbelt when operating equipment. |  |  | Tuesday - Victory - Guard missing on grinder. Worker needed taller ladder for use and ladder not used on a stable base (wooden plank). Friday - No violations found |  |  | One guardrail 2x4 was cracked in the middle - HB superintendent notified and this was fixed by Victory during walk. | All Edrian Steel workers observed tied off/with proper gates closed while working.
Els School for Autism |  |  |  |  | 100% | 99.8% + 89% | 94.2% + 99.8% | 100% + 98% | 100% | 100%
[6 empty] | Tuesday -Craig has been reminded of DAILY sign in requirements. Thursday- Fencing gate panels near golf course not properly secured, protective screening may need to be replaced due to large holes exposing views to children. CTP Masonry scaffolding missing inspection tag. CTP Mason observed standing on top of A frame ladder. He was told not to stand on top and to get taller ladder if necessary. CTP Masonry scaffolding missing base plate, foreman said base plate as well as mudsills were ordered and on the way to site. Extension cord running across drive pathway connected to generator showing signs of damage. Multiple employees were spoken to about smoking on site. The gate guard was supplied with a tent, table, and folding chair. He is to be signing in EVERY single person he sends through the gat. HB included. | Tuesday- Scaffolding inspected and cleared for use. Working on getting green tags. Two H&H workers were found smoking on site, they were stopped and reminded of no smoking rules when on site. No smoking signs also delivered today and will be put up around site. Friday- Four panels on fence near golf course not properly secured. Panels need to be properly secured together. No smoking signs delivered to site, signs to be distributed around site by EOD Monday 3/30. | Friday - CTP using A-frame leaned up against column. Ladder was changed out during visit. |  | Scaffold being erected during visit - competent person to sign off and green tag once done.
Boynton Beach Tropical | 91.7% | 91.9% + 94.2% | 89% | 91.2% | 89.5% + 94.4% | 92.2% + 89.5% | 89.5% |  | 91.6% | 94.4%
| OSHA 300A and Emergency Contact lists missing. Alf bringing to site this week. Hardhat use not in compliance across project. Roof has exposed leading edges. Dorado and Division 8 had improper fall protection. Improper ladder use by the plumbers. Diesel tanks not stored properly. | Monday -OSHA 300A and emergency contacts have been posted. Housekeeping needs to be maintained throughout the jobsite. Hard hat use is an ongoing issue. Doardo's lack of fall protection needed to be addressed more then once, along with their scaffolding not being erected properly - missing baseplates. Thursday- Cleanup crews actively working. Hard hats not in use throughout project. Painter observed working without fall protection. Power design improperly using ladders, causeing trip hazards in halways with multiple extention cords, and operating forklift without seatbelt. | Hardhats were not being worn throughout the building by multiple subs. Employees working on the road must be wearing high visibility class 2 vests. "Fall Pro beyond this point" signs are missing on 2nd and 3rd floor sliding doors to balconies where railings have not been installed. Boom lift operator seen using improper fall protection. Division 8 employee improperly using a ladder. Stucco team is using scaffolding that is improperly erected. Materials have been left on balconies posing a fall hazard. Equipment operator not utilizing seatbelt. | Wednesday - Hardhats were not being worn throughout the bldg by multiple subs. The 2nd and 3rd floor balconies have open sliding glass doors with no "fall protection required beyond this point" signs, exposing leading edges. Ladder useage throughout the jobsite needed to be addressed; aluminum ladders were removed. Confined space work in a inactive manhole was supervised and safety protocols were in place. Gas monitors are used before entry. Items were reviewed with responsible trades and site supervision. Corrective measures were implemented in the field. Friday - Hardhats continue to be an issue. Painters utilizing boom lifts were corrected on their fall protection use. Framers were advised to lock baker scaffold before use. | Tuesday - All subcontractors have at least one employee with no hard hat. An employee was see using a grinder without a guard or proper PPE. Stucco and painters both improperly using fall protection in boom lifts. Drywall crew was advised to remove all aluminum ladders. Dorardo was corrected on their scaffold erection. Friday - Hardhats have been strictly enforced! Extension cords in hallways were reorganized to avoid damage and trip hazards.3rd flood lighting hanging low. | Tuesday - Dorador wire lather was observed working on a boom lift with lanyard unattached to anchor point. Talbot Painter was not able to identify approved anchor points. He was attached to a tool slot. Screw jacks must be nailed down to mud sills. The Dorado scaffolding crew was advised. Lvl 3 has temp lights hanging too low. Dorado concrete mixer has a damage recoil starter. This needs to be repaired and engine to be closed at all times. Thursday- Hardhats were strictly enforced and housekeeping is active and in progress! Dorador plaster was observed working on a boom lift with lanyard unattached to anchor point. Dorado wirelather was observed using A frame ladder closed.Dorado Wirelather has an Aluminum ladder on site. Screw jacks must be nailed down to mud sills. The Dorado scaffolding crew was advised of the repeated offense. Dorado framer was advised to use wheel locks at all times. Dorado framer was advised to use 16guage or heavier. Dorado concrete mixer has a damage recoil starter. This needs to be repaired and engine to be closed at all times. (Repeated offence) Power Design needs to use sweeping compound when doing housekeeping. Two Dorado employees were observed working on buckets. | BDA & ABH Air Conditioning had employees with no hardhat. Hardhat required is strictly enforced. National employee was advised to use safety glasses when using table saw. Dorado crew was observed working on a boom lift with lanyard unattached to anchor point. (Repeated offense) Power Design employee was observed using an A frame ladder closed, leaning against the wall. Corrective action taken. Screw jacks must be nailed down to mud sills. The Dorado scaffolding crew was advised. (repeated offence) All American Glass was advised of incorrect use of a GFCI. Corrective actions made. Unidentified extension cords with missing ground prong, have been removed and put out of service. Block mason was advised of plastic gas containers prohibited on all HB projects. Metal containers only. Employees in violation regarding fall protection and no hard hat equipped had been advised repeated offences will result in employees sent home. The HB team has continued and established safety efforts and expectations. Safety violations identified during the inspection were addressed with the responsible subcontractors, following corrective action. | Monday - Balconies on the 3/2nd floor need fall protection signs. Screw jacks must be nailed down to mud sills. The Dorado scaffolding crew was advised. (repeated offence). Power Design forklift operator must wear his seatbelt before moiving materials and equipment. | Housekeeping is active and in progress. New Dorado employees were reminded to equip hardhat at all times. Power Design & Ridgeway Plumbing Employees were reminded the scissor lift gate must be closed at all times. Power Design employee was advised to open A frame ladder before use. Extension cords with missing ground prong were reported. Dorado Drywall employees were advised to organize extension cords and prevent trip hazards. Corrective action taken.Power Design forklift operator must wear his seatbelt before moiving materials and equipment. | General Property & New Dorado employees were reminded to equip hardhat at all times. Dorado employee was observed sanding compound with the required PPE. Power Design employee was advised to open A frame ladder before use. Dorado scaffolding on the south end is missing braces and a red tag to prevent further use. Overall, the site is making solid progress. Thank you for maintaining a safe and productive work environment.
Safe Harbor | 98.9% | 98.9% | 93.4% | 97.8% | 98.6% & 100% | 98.3% | 97.1% + 96.9% + 90.4% | 96.9% + 100% | 96.9% | 96.9%
| 1 employee was observed with his hardhat next to him rather than on his head. Correction Made. | Grinder was removed from use due to lack of guard. | Roofer missing fall protection, framer missing eye protection while cutting, low rated extension cord removed from service. A stand down was conducted to address the safety expectations and complacency during the fast paced work. | Victory missing guard on grinder, grinder was taken out of service until guard is put on. Paving crew cutting not using water, workerswere stopped and asked to use water beforecutting. | Monday - 2 drywall employees reminded to don hardhats. Friday - No issues found! | Titan tile worker operating boom lift without wearing a harness. | Monday - 1 Renco, 2 ECSI workers not wearing hardhat. The roofing foreman was observed not wearing harness on roof. Thursday- One Rodrigues finisher and one Talbot painter found not wearing hardhat during walk. 2 Titan tile workers found with guard off of grinder. Titan tile worker operating aerial lift did not have leg straps fastened. Friday- Lighting in East stairway out. HB superintendent notified - awaiting electrical inspection by end of day to get permanent power on. One Rodrigues finisher and multiple workers on second floor not wearing hardhat. All were stopped and told to put on. Worker operating aerial lift was wearing harness, but was not tied off. He was stopped and told to tie of. Talbot's scissor lift missing gate/chain. Spoke with and will order chain replacement. Rodrigues found using plank from scissor lift to baker scaffolding to hold material as well as using ladder on baker scaffolding. They were stopped and told to remove ladder and planks immediately. HB Superintendent also addressed subs to correct the matter. One worker found straddling ladder. One low voltage guy standing on top of A-frame. Both stopped and told to use proper procedure and get taller ladder. Complete Heating and Cooling has an aluminum ladder on 2nd floor. Roofers has aluminum ladder on north side of building. Both need to be removed from site. | Monday - Serveral employees not wearing hardhats on the second floor. Hardhats are still enforced throughout site. A worker was seen using a grinder without a guard. Titan tile worker was corrected on harness use. Thursday- Construction safety was in order. please keep an eye on Safe Harbor Workers for PPE. | Monday- ECSI worker not wearing hardhat.Titan tile worker operating aerial lift had harness and lanyard on, but not tied off. | Welch worker operating aerial lift was observed not tied off and without leg pieces secured. Miller glass observed using aluminum ladder.
Family Church | 94% | 98.5%
| OSHA Posters misplaced during office move. Hardhats missing from multiple employees. Electrical room door was left open. Subcontractors have been addressed. | OSHA posters were misplaced during office move.
299 Golden Beach | 100% | 98.4% |  | 100% | 98.8% | 100% | 100% | 100% |  | 98.3%
|  | Plastic gas can was removed from site. |  |  | Worker using grinder without a guard in place. |  |  |  |  | Some angled rebar uncapped - happened during grading. Rebar was recapped during visit. Plumbers not wearing hard hats
19 Indian Creek | [6 empty] | 100% | 100% |  | 100%