## Summary Sheet
PROJECT NAME: | [6 empty] | Date: |  | Notes
PROJECT NO.: |  |  |  |  | PM: |  | SUPER:
Contract Type: |  | (CM / GMP / Lump Sum / Cost +) |  |  |  | Builders Risk Date:
Project Type: |  | New | Renovations |  |  | NOC Exp. Date:
Damage Clause/ LD's: |  |  | 0 | Per |  | Day
1 | SCHEDULE:
| Original Contract Compl.: |  |  |  |  | Current Schedule Data Date:
| Approved Days: |  | 0 |  |  | Current Completion Date:
| Revised Contract Compl.: |  |  |  |  | Current Damage Costs:
2 | FINANCIAL STATUS:
| Original Contract Value: |  | 0 | This includes Precon |  | Current Approved Value: |  | 0
Forecast | Original Cost: |  | 0 |  |  | Current Cost to Complete: |  | 0 | See Cost to Complete column in Procore
| Original Profit: |  | 0 |  |  | Current Profit: |  | 0 | Should match Procore profit (over/under column)
| Orig. Buyout Savings |  | 0 |  |  | Last Month Profit: |  | 0 | Line J13 from previous month's forecast
[6 empty] | Buyout Savings |  | 0 | Keep at $0 until buyout is complete at 60 days.
3 | CONTINGENCIES: |  |  |  |  | Buyout Savings Split |  | 0 | Contract terms need to be verified on savings clause.
| Original Contingency: |  | 0 |  |  | Contingency Savings |  | 0 | Add note for contingency requirements per Prime Contract (50/50, 100%, return to Owner)
| Current Contingency: |  | 0 |  |  | Potential Total Profit |  | 0 | Includes Current Profit + potential forecasted savings (buyout, contingency, etc.).
| Expected Contingency at Completion: |  | 0 |  |  | Previous Month Potential Profit |  | 0 | Line J17 from previous month's forecast
| Expected Contingency Use: |  | 0
4 | GENERAL CONDITIONS PERIOD ENDING:
| Original Estimate |  | 0
| Estimate at Completion: |  | 0 | [5 empty] | Should match GC log/ Procore
| Variance from Original |  | 0 | [5 empty] | Variance is a formula, not manual entry
5 | PROFIT FORECAST SUMMARY:
6 | PROBLEMS/EXPOSURES:
Schedule:
Budget:
Payment:
Safety:
RFI Log:
Submittal Log:
Buyout Log:
Risk Mgmt:
Change Orders:
Permits:
Critical Issues:

## Forecast Checklist
Monthly Forecast Checklist
📋 | Required Documents (printed)
Procore Budget – Updated and reconciled
Forecast Summary Sheet – Reflecting current and projected financials
GC/GR Log – Aligned with current schedule. Matches Summary sheet and Procore.
Cash Flow Schedule – Accurate through current PA #
SDI Tracking Log (also included in buyout log)
Buyout Log – With % bought out and lead time issues noted
📈 | Profit Forecast Summary
Explain any changes in current profit and any negative values in the Procore budget.
Explain any changes in potential profit, including GC savings and buyout savings from the previous month.
Identify any projected items/events that may affect profit (e.g., staffing changes, scope changes)
📅 | Schedule
Brief summary of schedule status
Note anything brewing or actively affecting the schedule
Confirm GC/GRs match current schedule
List any delay notices issued or pending (include count)
Indicate if additional time is being requested via change order and why
💰 | Budget
Identify any budget-related problems or exposures
Review Job Cost History Report
💳 | Payment
Confirm payments received through [PA # / date]
Are payments on time?
Note any payment-related problems or exposures
🦺 | Safety
Count of open safety observations in Procore
Note any safety-related problems or exposures
📑 | RFI Log
List open RFIs that could affect budget and/or schedule
📦 | Submittal Log
List open submittals that could affect budget and/or schedule
🛒 | Buyout Log
Confirm current % bought out.
Date expected to be 100% bought.
Note any issues with lead times.
📋 | Risk Management
Confirm subcontractor compliance is up to date
List non-compliant subcontractors
Confirm % of SDI enrolled subcontractors
Note any risk-related problems or exposures
🔁 | Change Orders
List pending change orders, including time extensions and amounts
Confirm PCCO approvals
🏗️ | Permits
Provide status of permits and inspections with issue and/or delay.
🔍 | Rolling Punch List
Provide status of Procore Observations (rolling punch)
📋 | Project Checklists
Provide status of Job Start Up Checklist
Provide status of Pre-Certificate of Occupancy Checklist
Provide status of Project Close-out Checklist
🚨 | Critical Issues
Identify any current critical issues affecting the project
v1.0 (2025.8)
v1.1(2025.12)
v1.2(2026.2)