## Sheet1
PROJECT NAME RFI SET# DATE
# | Topic | Question | Asking | Sent | To | Answer | Response Received | Forwarded
RFI SET 1
1 | Drawings | The drawing index on sheet CV-1 of the site set of plans references "Sheet 1 of 1 - Boundary & Topographic Survey." The survey was not attached in the drawings that were distrubuted to bidders. Please provide the Boundary & Topographic Survey. | Hedrick Brothers | 2017-04-19 |  |  | YES | YES
2 | Pavers | Utility Drawing 6 of 9 indicates a different layout for the pavers than shown on drawing HS-1. Are we to follow drawing HS-1? | Hedrick Brothers | 2017-04-19 |  |  | YES | YES
3 | Pickleball Courts | Drawings HS-1, Utility 6 of 9 and Paving, Grading & Drainage Plan 5 of 9 all indicate what appears to be viewing stands on the east side of the new courts. Are these new viewing stands? and if so please provide a specification for same. | Hedrick Brothers | 2017-04-19 |  |  | YES | YES
4 | Pool Deck Pavers | Please provide a section detail for the Pool Deck Pavers. Include information regarding paver thickness, base material composition and compaction, and whether or not the pavers are installed over a concrete slab. | Hedrick Brothers | 2017-04-19 |  |  | YES | YES
5 | Geotech Report | The borings taken for the geotechnical report dated 8/24/16, represent a site/building layout which has changed. Will a new report be issued to reflect the revised building/site layout? Please advise | Hedrick Brothers | 2017-04-19 |  |  | YES | YES
6 | Rain Gutters | Please advise what material the K style gutters are. | Hedrick Brothers | 2017-04-19 |  |  | YES | YES
7 | Metal Louvers | Please advise if decorative wall mounted metal louvers are aluminium and if so are they powder coated? Is this finish typical for all buildings? | Hedrick Brothers | 2017-04-19 |  |  | YES | YES
8 | Wood Outlookers | Please advise the grade of cedar for the exterior wood outlookers for all buildings. Please also confirm the cedar is to be "Western Red Cedar". | Hedrick Brothers | 2017-04-19 |  |  | YES | YES
9 | Exterior Wood T&G Ceiling | Please advise species and grade of exterior T&G for all buildings. | Hedrick Brothers | 2017-04-19 |  |  | YES | YES
10 | Equipment Screening | Sheet A2.02 East and North Elevation shows a decorative powder coated aluminium louver that is to be removable. Please advise on a connection detail that will meet any required NOA by Martin County. | Hedrick Brothers | 2017-04-19 |  |  | YES | YES
11 | Wood Fascia and Drip edge | Please advise the species and grade of exterior wood fascia and drip edge for all buildings. | Hedrick Brothers | 2017-04-19 |  |  | YES | YES
12 | Ceramic Tile | Please provide elevations depicting the location(s) for the CT-3 wall tile in the dining . None have been provided in the bid docs. | Hedrick Brothers | 2017-04-19 |  |  | YES | YES
13 | Swimming Pool | Please provide design details for new lagoon pool and aquatic fitness pool or an allowance for both. | Hedrick Brothers | 2017-04-19 |  |  | YES | YES
14 | Shade Structure at Pool | Please provide design details for the 12'x14' shade structures surrounding the pool shown on sheet A0.01 of the Pool Bar & Grill drawing set. | Hedrick Brothers | 2017-04-19 |  |  | YES | YES
15 | Interior Trim | Please specify species and grade of all interior trim. | Hedrick Brothers | 2017-04-19 |  |  | YES | YES
16 | Kitchen Equipment | Please provide kitchen equipment proposal for review to ensure there are no gaps between the MEP contractors. | Hedrick Brothers | 2017-04-19 |  |  | YES | YES
RFI SET #
1
2
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36