## Sheet1
HEDRICK BROTHERS CONSTRUCTION
COMMERCIAL DIVISION OPERATIONS
2026-03-17
EMPLOYEE | POSITON | PROJECT | 2019 | [6 empty] | 2020 | [10 empty] | 2021 | [10 empty] | 2022 |  |  |  | 2026 | [11 empty] | 2027
|  |  | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | FEB | MAR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | ARIL | MAY | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN
Duke Snyder
Duke Snyder | PEX | Oculus | [28 empty] | Precon | Precon | Precon | Precon | 2026 MAR: Pending litigation
Yolanda Donado | APM | Oculus | bar: MAY to 2026 JAN
Duke Snyder | PEX | Volusia MSC | [32 empty] | 2026 MAR: Final Payment
Betty Jo Yorio | Proj Acct | Volusia MSC | [32 empty] | 2026 MAR: Also on Tropical and WinterSprings
Monica Crowley | PA | Volusia MSC | [32 empty] | 2026 MAR: Also on Pratt and MDC
Duke Snyder | PX | Parrish Medical | [32 empty] | 2026 MAR: Final Payment
Duke Snyder | PM | Parrish Medical | bar: MAY to 2026 FEB
Betty Jo Yorio | PA | Parrish Medical | bar: MAY to 2026 FEB
Duke Snyder | PX | VS Fire Station 22 | [32 empty] | 2026 APR: April
Duke Snyder | PM | VS Fire Station 22 | [32 empty] | 2026 APR: Groundbreak
Betty Jo Yorio | PA | VS Fire Station 22
Jimmy McCullough | Super | VS Fire Station 22 | bar: MAY; 2026 MAR to 2027 JUN
Duke Snyder | PX | FIT Bridge
Duke Snyder | PM | FIT Bridge | [32 empty] | 2026 DEC: GB November
Betty Jo Yorio | PA | FIT Bridge | bar: MAY; 2026 NOV to 2027 JUN
| Super | FIT Bridge | bar: MAY; 2026 NOV to 2027 JUN
Arthur Miller
Arthur Miller | PEX | Pratt - B 100 Olympus | [32 empty] | 2026 JAN: complete CO work
Monica Crowley | P Acct | Pratt - B 100 Olympus | [32 empty] | 2026 JAN: complete CO work
Shlighton Estime | Lead PM | Pratt - B 100 Olympus | [32 empty] | 2026 JAN: complete CO work; 2026 JUN: To The Modern
Tyler Everett | Lead Super | Pratt - B 100 Olympus | [32 empty] | 2026 JUN: To The Modern
Joe Trimarco | Super | Pratt - B 100 Olympus | [32 empty] | 2026 JAN: complete CO work
Jalill Talley | Laborer | Pratt- B 100 Olympus | [32 empty] | 2026 JUN: To The Modern
Eric Carlson Jr. | Asst. Super | Pratt - B 100 Olympus | [32 empty] | 2026 JAN: complete CO work
Joe Keating
Joe Keating | PEX | Wynnebrook ES | bar: 2026 JAN
Tony Mish | PM | Wynnebrook ES | [32 empty] | 2026 FEB: Helping with Keiser, working on Temp school pricing for Wynnbrook
Eric Hudson | Super | Wynnebrook ES | [32 empty] | 2026 SEP: Cafeteria rework
Michelle Carlson | P Acct | Wynnebrook ES | [32 empty] | 2026 FEB: To Residential
Joe Keating | PEX | Cardinal Newman PH 2
Justin Molina | PM | Cardinal Newman PH 2 | bar: MAY; 2026 OCT to 2027 JUN
| PA | Cardinal Newman PH 2 | bar: MAY; 2026 OCT to 2027 JUN
Mike Morris | Super | Cardinal Newman PH 2 | bar: 2026 OCT to 2027 JUN
Joe Keating | PEX | Cardinal Newman Athletic Area | bar: MAY to 2026 OCT
Justin Molina | PM | Cardinal Newman Athletic Area | bar: MAY; 2026 APR to 2026 OCT
| PA | Cardinal Newman Athletic Area | bar: MAY; 2026 APR to 2026 OCT
Mike Morris | Super | Cardinal Newman Athletic Area | [32 empty] | 2026 JUL: 4-5 month duration
Joe Keating | PEX | Stuart Middle School | [32 empty] | 2026 MAR: Final Payment
Ben Coats | PM | Stuart Middle School | [32 empty] | 2026 MAR: To Murray
Tacara Hickman | P Acct | Stuart Middle School | [32 empty] | 2026 MAR: To Murray - also on Caretta
Joe Keating | PEX | YMCA | bar: MAY to 2026 NOV
Dave Rawdon | PM | YMCA | bar: MAY to 2026 NOV
Tom Holt | Super | YMCA | bar: MAY to 2026 NOV
Tanya Stiles | PA | YMCA | bar: MAY to 2026 NOV
Joe Keating | PEX | Murray Middle School | bar: MAY to 2026 DEC
Ben Coats | PM | Murray Middle School | bar: MAY to 2026 DEC
| APM | Murray Middle School | bar: MAY to 2026 DEC
Francois Depreist | Super | Murray Middle School | bar: MAY; 2026 AUG to 2026 DEC
Ron Greene | Super | Murray Middle School | [32 empty] | 2026 JUN: May/June GB
Gonzalo Zapata | Laborer | Murray Middle School | bar: MAY; 2026 AUG to 2026 DEC
| Laborer | Murray Middle School | bar: MAY; 2026 AUG to 2026 DEC
Tacara Hickman | P Acct | Murray Middle School | bar: MAY to 2026 DEC
Joe Keating | PX | Keiser Student Housing
Bill West | Sr. PM | Keiser Student Housing
Tony Mish | PM | Keiser Student Housing | [32 empty] | 2026 MAR: Feb GB
| APM | Keiser Student Housing
Jill Voorhees | Proj Acct | Keiser Student Housing
Stacy Helmes | PA | Keiser Student Housing
Rene Fernandez | Lead Super | Keiser Student Housing | bar: MAY; 2026 APR to 2027 JUN
Ronnie Poliseo | 2nd Super | Keiser Student Housing
| 3rd Super | Keiser Student Housing | bar: MAY; 2026 JUN to 2027 JUN
| Asst. Super | Keiser Student Housing
Joe Keating | PX | Keiser STEM Building
Bill West | Sr. PM | Keiser STEM Building | [32 empty] | 2026 JUN: June GB
| PM | Keiser STEM Building | bar: MAY; 2026 MAR to 2027 JUN
| APM | Keiser STEM Building | bar: MAY; 2026 MAR to 2027 JUN
Jill Voorhees | Proj Acct | Keiser STEM Building | bar: MAY; 2026 MAR to 2027 JUN
Stacy Helmes | PA | Keiser STEM Building | bar: MAY; 2026 MAR to 2027 JUN
| Lead Super | Keiser STEM Building | bar: MAY; 2026 JUN to 2027 JUN
Ronnie Poliseo | 2nd Super | Keiser STEM Building | bar: MAY; 2026 JUN to 2027 JUN
| Asst. Super | Keiser STEM Building | bar: MAY; 2026 JUN to 2027 JUN
Joe Keating | PX | Keiser Primrose Playground | bar: MAY
Justin Molina | PM | Keiser Primrose Playground | [32 empty] | 2026 JUN: Summer
| Super | Keiser Primrose Playground | bar: MAY
Stacy Helmes | PA | Keiser Primrose Playground | bar: MAY
Bob Cashin
Bob Cashin | PEX | NORA | bar: 2026 JAN to 2026 FEB
Bill West | PM | NORA | [32 empty] | 2026 MAR: To Keiser
Laura Ratliff | APM | NORA | [32 empty] | 2026 MAR: To Eau
Brad Harrison | Super | NORA | [32 empty] | 2026 JUN: To Ibis
Eric Hudson | Super | NORA | [32 empty] | 2026 MAR: To Wynnbrook, then Eau
Jill Voorhees | P Acct | NORA | [32 empty] | 2026 MAR: To Keiser, Also at Family Church
Jorge Postigo | Carpenter | NORA | [32 empty] | 2026 MAR: To Waterview?
Dennis Marcinko | Carpenter | NORA | bar: 2026 JAN to 2026 FEB
Bob Cashin | PEX | Caretta | bar: 2026 JAN to 2026 AUG
Matt Cox | Sr. PM | Carretta | bar: 2026 JAN to 2026 AUG
Christina Boucher ? | PM | Caretta | bar: 2026 JAN to 2026 AUG
Pawan Wadhwani | PM | Caretta | bar: 2026 JAN to 2026 AUG
Hunter McElkyea | Jr. Est. | Caretta | [32 empty] | 2026 AUG: Back to estimating dept.
| PM | Caretta | bar: 2026 FEB to 2026 AUG
| APM | Caretta | bar: 2026 FEB to 2026 AUG
Yolanda Donado | APM | Caretta | bar: 2026 JAN to 2026 AUG
Sam Kunaugh | PA | Caretta | [32 empty] | 2026 JUL: SC; 2026 AUG: CO; 2026 SEP: To One Island Way for Residential
Tacara Hickman | P Acct | Caretta | [32 empty] | 2026 JUL: SC; 2026 AUG: CO; 2026 SEP: Murray Middle School
JT Torres | General Sup | Caretta | [32 empty] | 2026 JUL: SC; 2026 AUG: CO; 2026 SEP: To One Island Way for Residential
Ron Greene | 6th Super | Caretta | [32 empty] | 2026 JUL: Murray Middle School
Chris Carr | 2nd Super | Caretta | bar: 2026 JAN to 2026 AUG
Dante Rolle | 3rd Super | Caretta | bar: 2026 JAN to 2026 AUG
Francois Depreist | 4th Super | Caretta | [32 empty] | 2026 SEP: Murray Middle School
Wally Ramcharran | 5th Super | Caretta | bar: 2026 JAN to 2026 AUG
Vinny Viaggio | Finish Super | Caretta | bar: 2026 APR to 2026 AUG
Mardiel Cuesta | Asst. Super | Caretta | bar: 2026 JAN to 2026 AUG
| QC Tech | Caretta | bar: 2026 JAN to 2026 AUG
Akion Thomas | Laborer | Caretta | bar: 2026 JAN to 2026 AUG
Aiden Daly | Laborer | Caretta | bar: 2026 JAN to 2026 AUG
Eberson Merilien | Leadman | Caretta | bar: 2026 JAN to 2026 AUG
Gerry Ramcharran | Carpenter | Caretta | bar: 2026 JAN to 2026 AUG
| Laborer | Caretta | bar: 2026 JAN to 2026 AUG
Bob Cashin | PEX | Els Autism School | bar: MAY to 2027 APR
Amber Wangle | PM | Els Autism School | [32 empty] | 2026 FEB: GB 02/09/26; 2027 MAR: SC; 2027 APR: CO
Craig Nelson | Super | Els Autism School | bar: MAY to 2027 APR
Andy Guiterrez | Asst. Super | Els Autism School | bar: MAY to 2027 APR
Andrew Covel | PM1 | Els Autism School | bar: MAY to 2027 APR
Bob Cashin | PEX | Ibis Country Club | bar: MAY; 2027 JAN to 2027 JUN
Dave Rawdon | Sr. PM | Ibis Country Club | bar: MAY; 2027 JAN to 2027 JUN
Tanya Stiles | APM/PA | Ibis Country Club | bar: MAY; 2027 JAN to 2027 JUN
Brad Harrison | Lead Super | Ibis Country Club | [32 empty] | 2026 MAY: May Start
| Asst. Super | Ibis Country Club | bar: MAY; 2027 JAN to 2027 FEB; 2027 APR to 2027 JUN
| Super | Ibis Country Club - Spa | [32 empty] | 2027 JAN: GB January '27
| Asst Super | Ibis Country Club - Spa | bar: MAY
Matt Zaryk
Matt Zaryk | PEX | Perla - Tallahassee | bar: MAY to 2026 SEP
Jim Pearce | PM3 | Perla - Tallahassee | [32 empty] | 2026 AUG: SC; 2026 SEP: CO; 2026 NOV: Also on Hanging Moss
Steve Wackes | PM3 | Perla - Tallahassee | bar: MAY to 2026 SEP
Frederica Young | PM1 | Perla - Tallahassee | bar: MAY to 2026 SEP
Lori Shanks | P Acct | Perla - Tallahassee | bar: 2026 JAN to 2026 SEP
Kim Spivey | PA/PC | Perla - Tallahassee | bar: 2026 JAN to 2026 SEP
Patrick Rapport | APM | Perla - Tallahassee | bar: 2026 JAN to 2026 SEP
Joe Caliendo | Lead Super | Perla - Tallahassee | [32 empty] | 2026 NOV: To Hilltop - WPB
Jacob Cowan | Super | Perla - Tallahassee | bar: 2026 JAN to 2026 SEP
Frank Bobco | Super | Perla - Tallahassee | [32 empty] | 2026 NOV: To Bath and Racquet
Michelle Wortham | Super | Perla - Tallahassee | bar: 2026 JAN to 2026 SEP
Mathew Balkcom | Asst Super | Perla - Tallahassee | bar: 2026 JAN to 2026 SEP
Matt Zaryk | PEX | Hanging Moss - Orlando | bar: MAY; 2027 JAN to 2027 JUN
Dan Miller | Sr. PM | Hanging Moss - Orlando | bar: MAY; 2027 JAN to 2027 JUN
Jim Pearce | PM | Hanging Moss - Orlando | bar: MAY; 2027 JAN to 2027 JUN
Clayton Kolar | APM/PA | Hanging Moss - Orlando | bar: MAY; 2027 JAN to 2027 JUN
Lori Shanks | P Acct | Hanging Moss - Orlando | bar: MAY; 2027 JAN to 2027 FEB; 2027 APR to 2027 JUN
Chris Lineberger | Lead Super | Hanging Moss - Orlando | bar: MAY; 2027 JAN to 2027 FEB; 2027 APR to 2027 JUN
Lucio Salcedo | Super | Hanging Moss - Orlando | bar: MAY
| Asst Super | Hanging Moss - Orlando | bar: MAY
Matt Zaryk | PEX | Kissimee- JYP
Dan Miller | PM | Kissimee- JYP | [32 empty] | 2026 APR: April GB
Clayton Kolar | APM | Kissimee- JYP | bar: MAY; 2026 APR to 2027 JUN
Betty Jo Yorio | P Acct | Kissimee- JYP | bar: MAY; 2026 APR to 2027 JUN
| PA/PC | Kissimee- JYP | bar: MAY; 2026 APR to 2027 JUN
Craig Stephens/Mark Ozee | Lead Super | Kissimee- JYP | bar: MAY; 2026 APR to 2027 JUN
| Super | Kissimee- JYP | bar: MAY; 2026 APR to 2027 JUN
| Asst Super | Kissimee- JYP | bar: MAY; 2026 APR to 2027 JUN
Brent Barnes
Brent Barnes | PEX | Winter Springs | bar: MAY to 2027 APR
Colin Daughtery | PM | Winter Springs | bar: MAY to 2027 APR
| APM | Winter Springs | bar: MAY to 2027 APR
Betty Jo Yorio | P Acct | Winter Springs | bar: MAY to 2027 APR
Craig Daugherty | Lead Super | Winter Springs | bar: MAY to 2027 APR
| Asst Super | Winter Springs | bar: MAY to 2027 APR
Brent Barnes | PX | Bath and Racquet Tampa | bar: MAY to 2026 DEC; 2027 MAR to 2027 JUN
| PM | Bath and Racquet Tampa | bar: MAY; 2026 AUG to 2026 DEC; 2027 MAR to 2027 JUN
Frank Bobco | Super | Bath and Racquet Tampa | [32 empty] | 2026 MAY: 10 month schedule
| PA | Bath and Racquet Tampa | bar: MAY; 2026 AUG to 2026 NOV; 2027 MAR to 2027 JUN
Paul Fulks
Paul Fulks | PEX | Waterview Apt - Mangonia
Brian Krpata | PM | Waterview Apt - Mangonia
Laura Ratliff | APM | Waterview Apt - Mangonia | bar: 2026 APR to 2027 JUN
Brian Venezia | Super | Waterview Apt - Mangonia | bar: 2026 APR to 2027 JUN
| Asst. Super | Waterview Apt - Mangonia | bar: 2026 APR to 2027 JUN
| Proj Acct | Waterview Apt - Mangonia | bar: 2026 APR to 2027 JUN
Paul Fulks | PEX | Safe Harbor | bar: MAY to 2026 APR
Bob Joy | PM | Safe Harbor | [32 empty] | 2026 MAR: SC; 2026 APR: CO; 2026 MAY: To Waterview
Rene Fernandez | Super | Safe Harbor | [32 empty] | 2026 MAR: SC; 2026 APR: CO; 2026 MAY: To Keiser
Kevin Waterrud | Super | Safe Harbor | [32 empty] | 2026 MAR: SC; 2026 APR: CO; 2026 MAY: To Safe Harbor 3rd Floor or Keiser Primrose
Mike Morris | Super | Safe Harbor | [32 empty] | 2026 MAY: To Cardinal
Rylan Vickery | Apprentice | Safe Harbor | [32 empty] | 2026 MAY: To Hilltop
Justin Molina | APM | Safe Harbor | [32 empty] | 2026 MAR: SC; 2026 APR: CO; 2026 MAY: To Cardinal
Michelle Carlson | P Acct | Safe Harbor | [32 empty] | 2026 MAR: SC; 2026 APR: CO; 2026 MAY: To Residential
Paul Fulks | PX | Family Church | bar: MAY to 2026 MAR
Boris Lopez | PM | Family Church | [32 empty] | 2026 APR: Also on FCC, to Caretta
Jill Voorhees | PA | Family Church | [32 empty] | 2026 APR: To Keiser
Vinny Viaggio | Super | Family Church | [32 empty] | 2026 APR: To Caretta
Sam Platovsky | Asst. Super | Family Church | [32 empty] | 2026 APR: To Hilltop
Bobby Fetting
Bobby Fetting | PX | The Modern - PGA Station
Shlighton Estime | PM | The Modern
Andrew Edwards | APM | The Modern
Monica Crowley | Proj Acct | The Modern | [32 empty] | 2026 APR: 04/17 Groundbreak
| PA | The Modern
Tyler Everett | Lead Super | The Modern | bar: MAY; 2026 MAR to 2027 JUN
Eric Carlson Jr. | Asst. Super | The Modern | bar: MAY; 2026 JUN to 2027 JUN
Jalill Talley | Laborer | The Modern | bar: MAY; 2026 MAR to 2027 JUN
Bobby Fetting | PEX | Boynton Beach Tropical | bar: MAY to 2026 OCT
| PM | Boynton Beach Tropical | bar: 2026 JAN to 2026 OCT
Fred Mangum | Lead Super | Boynton Beach Tropical | bar: 2026 JAN to 2026 OCT
Anthony Lilly | 3rd Super | Boynton Beach Tropical | [32 empty] | 2027 JAN: To Hilltop
Eric Carlson | 2nd Super | Boynton Beach Tropical | bar: 2026 JAN to 2026 OCT
Rameau Morency | Asst. Super | Boynton Beach Tropical | [32 empty] | 2027 JAN: To Hilltop
Greg Garvin | Lab/Carp | Boynton Beach Tropical | bar: 2026 JAN to 2026 OCT
Gonzalo Zapata | Laborer | Boynton Beach Tropical | [32 empty] | 2027 JAN: To Murray Middle
Milan Mistry | APM | Boynton Beach Tropical | [32 empty] | 2027 JAN: To Hilltop
Betty Jo Yorio | Proj Acct | Boynton Beach Tropical | [32 empty] | 2027 JAN: Also on VCFS, WS
Bobby Fetting | PEX | Kolter Hilltop
Brian Krpata | Sr. PM | Kolter Hilltop | [32 empty] | 2026 APR: May/June GB
Andrew Covel | PM | Kolter Hilltop | bar: 2026 APR to 2027 JUN
| PA | Kolter Hilltop | bar: 2026 APR to 2027 JUN
Joe Caliendo | Lead Super | Kolter Hilltop | bar: 2026 JUN to 2027 JUN
Anthony Lilly | 2nd Super | Kolter Hilltop | [32 empty] | 2026 NOV: Submitted schedule is 6 months after start
Sam Platovsky | Asst. Super | Kolter Hilltop | bar: 2026 JUN to 2027 JUN
Rameau Morency | Asst. Super | Kolter Hilltop | [32 empty] | 2026 NOV: Submitted schedule is 9 months after start
Jorge Postigo | Carpenter | Kolter Hilltop | bar: 2026 JUN to 2027 JUN
Rylan Vickery | Foreman | Kolter Hilltop | bar: 2026 JUN to 2027 JUN
Betty Jo Yorio | Proj Acct | Kolter Hilltop | bar: 2026 JUN to 2027 JUN
Jack Ullrich
Jack Ullrich | PEX | PBC MDC West Tower
John Richardson | Sr PM | PBC MDC West Tower
Yasser Ghareeb | APM | PBC MDC West Tower | [32 empty] | 2026 APR: Need replacement APM in July
John Varney | Super | PBC MDC West Tower
Victoria Miel | PA | PBC MDC West Tower
Monica Crowley | P Acct | PBC MDC West Tower
Jack Ullrich | PEX | PBC MDC Generator
Jordan Travanino | PM | PBC MDC Generator
Aric Brothers | Super | PBC MDC Generator
Monica Crowley | P Acct | PBC MDC Generator
Jack Ullrich | PEX | PBC MDC MDC AHU Switchout
Yasser Ghareeb | PM | PBC MDC MDC AHU Switchout | bar: MAY; 2026 MAR to 2027 JUN
Kevin Waterrud | Super | PBC MDC MDC AHU Switchout | [32 empty] | 2026 OCT: October Start
Monica Crowley | P Acct | PBC MDC MDC AHU Switchout
Possible Available Date |  | Project coming from:
Joe Trimarco | Super 1 | Pratt | [32 empty] | 2026 FEB: Pratt Compressor ?
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | [21 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jul | Aug | Sep | Oct | Nov | Dec