## Lessons Learned Form
LESSONS LEARNED REPORT
Hedrick Brothers Construction · Project Closeout Documentation
SECTION 1 — PROJECT IDENTIFICATION
| Project Name |  |  |  | Project Number
| Project Location / Address |  |  |  | Project Type
| Original Contract Value ($) |  |  | Final Contract Value ($) |  |  | Variance ($)
| Scheduled Completion |  |  | Actual Completion |  |  | Days Variance
| Project Manager |  |  | Superintendent |  |  | Project Executive
| Report Prepared By |  |  |  |  | Date of Report
SECTION 2 — PROJECT CLASSIFICATIONS (check all that apply — drives database filtering)
| Delivery Method |  | Market Sector |  |  | Project Size Band |  | Complexity Rating
| Design-Bid-Build |  | K-12 Education |  |  | Under $1M |  | 1 – Straightforward
| Design-Build |  | Higher Education |  |  | $1M – $5M |  | 2 – Moderate
| CM at Risk |  | Healthcare / Medical |  |  | $5M – $15M |  | 3 – Complex
| GMP |  | Government / Civic |  |  | $15M – $50M |  | 4 – Highly Complex
| Lump Sum |  | Office / Commercial |  |  | $50M – $100M |  | 5 – Exceptional
| IDIQ / Job Order |  | Industrial / Mfg |  |  | Over $100M
| Public-Private (P3) |  | Retail / Hospitality
Residential / Mixed-Use
Transportation / Infra
Data Center / Tech
Mission Critical
Renovation / Historic
Other
SECTION 3 — INDIVIDUAL LESSON ENTRIES (one block per distinct lesson)
INSTRUCTIONS: Complete one block per lesson. Use specific, actionable language. Rate applicability 1 (rarely applicable) to 5 (always applicable). Tag keywords that future teams will search for.
LESSON #1
Category |  | Select ▼ |  |  | Phase Encountered |  | Select ▼ |  | Applicability (1–5)
Keywords / Tags |  | e.g., concrete, footing, weather, permit delay — comma-separated
SITUATION — What happened?
Describe the specific condition or event. Include when, who, and what triggered it.
IMPACT — What were the consequences? | [6 empty] | Impact Magnitude |  | Select ▼
Quantify where possible: cost ($), schedule (days), safety, rework hours, relationship impact.
ROOT CAUSE — Why did it happen?
Identify the underlying cause: planning gap, communication failure, design deficiency, scope ambiguity, vendor failure, site conditions, resource constraint.
RESPONSE — How did we address it on this project?
Describe the corrective or mitigation actions taken. Who was involved? Was it effective?
RECOMMENDATION — What should future teams do differently?
Start with an action verb. Name an owner and project phase. Example: 'Require structural steel lead-time confirmation from 2 suppliers at GMP development. Assigned to: Estimating Lead.'
Supporting Documents / References |  | RFI numbers, CO numbers, photo file paths, schedule snapshots
LESSON #2
Category |  | Select ▼ |  |  | Phase Encountered |  | Select ▼ |  | Applicability (1–5)
Keywords / Tags |  | e.g., concrete, footing, weather, permit delay — comma-separated
SITUATION — What happened?
Describe the specific condition or event. Include when, who, and what triggered it.
IMPACT — What were the consequences? | [6 empty] | Impact Magnitude |  | Select ▼
Quantify where possible: cost ($), schedule (days), safety, rework hours, relationship impact.
ROOT CAUSE — Why did it happen?
Identify the underlying cause: planning gap, communication failure, design deficiency, scope ambiguity, vendor failure, site conditions, resource constraint.
RESPONSE — How did we address it on this project?
Describe the corrective or mitigation actions taken. Who was involved? Was it effective?
RECOMMENDATION — What should future teams do differently?
Start with an action verb. Name an owner and project phase. Example: 'Require structural steel lead-time confirmation from 2 suppliers at GMP development. Assigned to: Estimating Lead.'
Supporting Documents / References |  | RFI numbers, CO numbers, photo file paths, schedule snapshots
LESSON #3
Category |  | Select ▼ |  |  | Phase Encountered |  | Select ▼ |  | Applicability (1–5)
Keywords / Tags |  | e.g., concrete, footing, weather, permit delay — comma-separated
SITUATION — What happened?
Describe the specific condition or event. Include when, who, and what triggered it.
IMPACT — What were the consequences? | [6 empty] | Impact Magnitude |  | Select ▼
Quantify where possible: cost ($), schedule (days), safety, rework hours, relationship impact.
ROOT CAUSE — Why did it happen?
Identify the underlying cause: planning gap, communication failure, design deficiency, scope ambiguity, vendor failure, site conditions, resource constraint.
RESPONSE — How did we address it on this project?
Describe the corrective or mitigation actions taken. Who was involved? Was it effective?
RECOMMENDATION — What should future teams do differently?
Start with an action verb. Name an owner and project phase. Example: 'Require structural steel lead-time confirmation from 2 suppliers at GMP development. Assigned to: Estimating Lead.'
Supporting Documents / References |  | RFI numbers, CO numbers, photo file paths, schedule snapshots
LESSON #4
Category |  | Select ▼ |  |  | Phase Encountered |  | Select ▼ |  | Applicability (1–5)
Keywords / Tags |  | e.g., concrete, footing, weather, permit delay — comma-separated
SITUATION — What happened?
Describe the specific condition or event. Include when, who, and what triggered it.
IMPACT — What were the consequences? | [6 empty] | Impact Magnitude |  | Select ▼
Quantify where possible: cost ($), schedule (days), safety, rework hours, relationship impact.
ROOT CAUSE — Why did it happen?
Identify the underlying cause: planning gap, communication failure, design deficiency, scope ambiguity, vendor failure, site conditions, resource constraint.
RESPONSE — How did we address it on this project?
Describe the corrective or mitigation actions taken. Who was involved? Was it effective?
RECOMMENDATION — What should future teams do differently?
Start with an action verb. Name an owner and project phase. Example: 'Require structural steel lead-time confirmation from 2 suppliers at GMP development. Assigned to: Estimating Lead.'
Supporting Documents / References |  | RFI numbers, CO numbers, photo file paths, schedule snapshots
LESSON #5
Category |  | Select ▼ |  |  | Phase Encountered |  | Select ▼ |  | Applicability (1–5)
Keywords / Tags |  | e.g., concrete, footing, weather, permit delay — comma-separated
SITUATION — What happened?
Describe the specific condition or event. Include when, who, and what triggered it.
IMPACT — What were the consequences? | [6 empty] | Impact Magnitude |  | Select ▼
Quantify where possible: cost ($), schedule (days), safety, rework hours, relationship impact.
ROOT CAUSE — Why did it happen?
Identify the underlying cause: planning gap, communication failure, design deficiency, scope ambiguity, vendor failure, site conditions, resource constraint.
RESPONSE — How did we address it on this project?
Describe the corrective or mitigation actions taken. Who was involved? Was it effective?
RECOMMENDATION — What should future teams do differently?
Start with an action verb. Name an owner and project phase. Example: 'Require structural steel lead-time confirmation from 2 suppliers at GMP development. Assigned to: Estimating Lead.'
Supporting Documents / References |  | RFI numbers, CO numbers, photo file paths, schedule snapshots
LESSON #6
Category |  | Select ▼ |  |  | Phase Encountered |  | Select ▼ |  | Applicability (1–5)
Keywords / Tags |  | e.g., concrete, footing, weather, permit delay — comma-separated
SITUATION — What happened?
Describe the specific condition or event. Include when, who, and what triggered it.
IMPACT — What were the consequences? | [6 empty] | Impact Magnitude |  | Select ▼
Quantify where possible: cost ($), schedule (days), safety, rework hours, relationship impact.
ROOT CAUSE — Why did it happen?
Identify the underlying cause: planning gap, communication failure, design deficiency, scope ambiguity, vendor failure, site conditions, resource constraint.
RESPONSE — How did we address it on this project?
Describe the corrective or mitigation actions taken. Who was involved? Was it effective?
RECOMMENDATION — What should future teams do differently?
Start with an action verb. Name an owner and project phase. Example: 'Require structural steel lead-time confirmation from 2 suppliers at GMP development. Assigned to: Estimating Lead.'
Supporting Documents / References |  | RFI numbers, CO numbers, photo file paths, schedule snapshots
SECTION 4 — PROJECT-LEVEL SUMMARY RATINGS
Rate overall performance in each domain (1 = Far Below Expectations → 5 = Far Exceeded Expectations)
Performance Domain |  |  |  |  | Notes / Evidence |  |  |  | Score (1–5)
Safety Performance |  |  |  |  | Incidents, near-misses, culture, subcontractor compliance
Quality & Craftsmanship |  |  |  |  | Punch list density, rework rate, first-time inspection pass rate
Schedule Adherence |  |  |  |  | On-time delivery, milestone reliability, float management
Cost / Budget Performance |  |  |  |  | Variance to GMP, contingency use, change order volume
Owner Satisfaction |  |  |  |  | Relationship quality, communication, trust, repeat likelihood
Subcontractor Management |  |  |  |  | Selection, oversight, performance management, issues resolved
Preconstruction Effectiveness |  |  |  |  | BIM, coordination, VE ROI, constructability reviews
Team Collaboration |  |  |  |  | Internal communication, problem-solving, escalation quality
Innovation / Best Practices |  |  |  |  | New methods, technology, or processes piloted
Overall Project Success |  |  |  |  | Holistic — would you want this project in your portfolio again?
OVERALL PROJECT PERFORMANCE AVERAGE
SECTION 5 — BEST PRACTICES TO REPLICATE
What worked so well it should become standard HBC practice? These entries feed the HBC Best Practice Library.
Best Practice #1 — Title | [6 empty] | Category
Describe the practice or process. Why did it work? What conditions are required? Who should own rollout?
Best Practice #2 — Title | [6 empty] | Category
Describe the practice or process. Why did it work? What conditions are required? Who should own rollout?
Best Practice #3 — Title | [6 empty] | Category
Describe the practice or process. Why did it work? What conditions are required? Who should own rollout?
SECTION 6 — PROCESS IMPROVEMENT RECOMMENDATIONS
Flag changes to HBC systems, standards, templates, or processes that would prevent recurrence company-wide.
Recommended Change |  |  |  |  | Owner / Department |  | Priority |  | Effort
[7 empty] | High / Med / Low |  | High / Med / Low
[7 empty] | High / Med / Low |  | High / Med / Low
[7 empty] | High / Med / Low |  | High / Med / Low
[7 empty] | High / Med / Low |  | High / Med / Low
[7 empty] | High / Med / Low |  | High / Med / Low
[7 empty] | High / Med / Low |  | High / Med / Low
SECTION 7 — REVIEW & APPROVAL
Project Manager | [6 empty] | Signature / Date:
Superintendent | [6 empty] | Signature / Date:
Project Executive | [6 empty] | Reviewed & Approved / Date:
VP of Operations | [6 empty] | Final Approval / Date:

## Lessons Database
LESSONS LEARNED DATABASE — HEDRICK BROTHERS CONSTRUCTION
One row = one lesson. Enter data after each form is completed. Use Excel Filter (Data → Filter) to search by category, project type, keywords, impact, etc.
# | Project Name | Project Number | Market Sector | Delivery Method | Project Size | Report Date | Lesson # | Category | Situation (What Happened) | Root Cause | Recommendation (Action Required) | Keywords / Tags | Impact Magnitude | Applicability (1–5)
1 | Riverside Office Park | 2023-087 | Office / Commercial | GMP | $15M–$50M | 2024-11-15 | 1 | SCHEDULE | Structural steel delivery delayed 6 weeks. Team assumed 10-week mill lead time; actual was 16 weeks at time of order. | Estimating used historical lead times without confirming current mill conditions. No procurement milestone established in schedule. | Require estimating to confirm current lead times with ≥2 steel suppliers at GMP development. Add structural steel procurement milestone to master schedule template. | steel, procurement, lead time, structural, schedule delay, estimating | Significant | 5
2 | Riverside Office Park | 2023-087 | Office / Commercial | GMP | $15M–$50M | 2024-11-15 | 2 | QUALITY | Concrete flatwork on floors 2–4 showed excessive surface cracking within 30 days of pour. Three areas required overlay at $41,000. | Subcontractor applied cure-and-seal too early, trapping bleed water. No third-party inspector present during finishing. | Require concrete subcontractor to submit flatwork quality plan including curing procedures. Mandate third-party special inspection for all elevated slabs >5,000 SF. | concrete, flatwork, cracking, curing, special inspection, rework, quality | Significant | 5
3 | Oakwood Medical Center | 2022-041 | Healthcare / Medical | CM at Risk | $50M–$100M | 2024-09-30 | 1 | OWNER / CLIENT | Owner changed room configuration for 14 patient rooms after MEP rough-in was 60% complete. Result: $287K in COs and 3-week delay. | No contractual design freeze milestone established. Team accepted verbal confirmation of design completion. | Establish a Design Freeze Milestone contractually before MEP rough-in. Include cost-escalation clause for changes after this date. | owner change, design freeze, MEP, scope creep, healthcare, change order | Critical | 5
DATABASE SUMMARY STATISTICS
Total Lessons Recorded |  |  |  | 3
Avg Applicability Rating
Count — Critical Impact |  |  |  | 1
Count — Significant Impact |  |  |  | 2
Count — Schedule Lessons |  |  |  | 1
Count — Safety Lessons |  |  |  | 0
Count — Quality Lessons |  |  |  | 1
Count — Cost / Budget Lessons |  |  |  | 0
Count — Subcontractor Lessons |  |  |  | 0
Count — Owner / Client Lessons |  |  |  | 1

## Reference Guide
LESSONS LEARNED — REFERENCE GUIDE & WRITING STANDARDS
LESSON CATEGORY DEFINITIONS |  |  | WRITING TIPS FOR HIGH-QUALITY LESSONS
Category | Definition & Examples |  | ✔ | Be SPECIFIC — name the trade, location, date, and dollar amount
PRE-CONSTRUCTION | Planning, scope development, constructability reviews, BIM coordination, owner alignment |  | ✔ | Be CAUSAL — explain WHY it happened, not just what happened
ESTIMATING & BID | Quantity takeoffs, bid strategy, allowances, unit price gaps, scope exclusions |  | ✔ | Be ACTIONABLE — recommendations name an owner and use an action verb
PROCUREMENT | Lead times, supplier qualification, subcontract terms, material escalation |  | ✔ | Avoid blame — focus on systems, processes, and conditions
SCHEDULE | CPM logic, float management, look-ahead reliability, milestone tracking |  | ✔ | Rate applicability honestly — not every lesson fits every project type
COST / BUDGET | Contingency use, change order management, GMP risk, buyout savings/losses |  | ✔ | One lesson per entry — don't combine unrelated issues
SAFETY | Incidents, near-misses, safety culture, PPE, subcontractor compliance, JHAs |  | ✔ | Tag thoroughly — use terms future teams will search
QUALITY | Rework, punch list density, inspection failures, mock-ups, material substitutions |  | ✔ | Link supporting documents by file path, RFI number, or CO number
SUBCONTRACTORS | Selection, performance, default, coordination issues, contract clarity |  | ✗ | DON'T write 'communication was poor' — describe what failed specifically
DESIGN / RFIs | Design gaps, RFI volume, architect responsiveness, drawing coordination |  | ✗ | DON'T omit cost/schedule data — quantification makes lessons actionable
OWNER / CLIENT | Scope creep, decision latency, design freeze, communication protocols |  | ✗ | DON'T wait until project end — capture lessons as they occur
TECHNOLOGY / BIM | BIM clash detection, drone use, project management software, digital twins
WORKFORCE / LABOR | Crew productivity, craft shortage, overtime, union issues, workforce development
COMMISSIONING | Systems startup, OAC sign-off, testing deficiencies, owner training, TAB
CLOSEOUT / TURNOVER | As-builts, O&Ms, warranties, attic stock, final lien waivers, COO
OTHER | Lessons not fitting above categories — describe in the narrative
IMPACT MAGNITUDE GUIDE
Rating | Threshold (Cost / Schedule) | Description
Minor | <$10K or <2 days | Isolated; resolved quickly with no lasting effect
Moderate | $10K–$50K or 2–10 days | Noticeable; required escalation; resolved without major disruption
Significant | $50K–$200K or 10–30 days | Material cost/schedule impact; required negotiation or recovery plan
Critical | >$200K or >30 days | Major impact; threatened milestone, budget, or safety compliance