## PM
[DATE] | RESPONSIBILITY MATRIX
Task Category | Tasks/Role | PX | Sr. PM | PM2 | PM1 | PA | QAQC | Proj Acct.
PX | Owner Notices (GC/Schedule) | X | Support
PX | Sign all contracts | X | Support | Support
PX | Sign all Prime contract change orders | X | Support | Support
PX | Sign all sub change orders above $10,000 | X | Support | Support
SPM | Sign all sub change orders below $10,000 |  | X | Support
SPM | Review & Approve Subcontractor SOV's |  | X
SPM | Review & Get Approved Change Orders (PCO, PCCO, CCO, PO, Inv's) | Sign-Off | X
SPM | Timberscan Invoice Approvals |  | X
SPM | Credit Card / Expense Report Approvals | Sign-Off | X
SPM | Get OCIP Subcontractor Credits Executed & Enrollment | Sign-Off | X
SPM | Complete Payment Application (Sub PA, Pencil, Final, Signatures) |  | X
SPM | Confirm Wire Timing & Approve Release of Funds |  | X
SPM | Monthly Financial Reports (GC/GR, Draw, Summary, Budget(s), Sage) | Sign-Off | X
SPM | Assemble & Update Schedule |  | X
SPM | Run Daily Internal Huddle Meeting |  | X
SPM | Run Project and collaborate with Team |  | X | Support | Support |  |  | Support
PM 2 | Update Subcontractor Tracking Sheet/Status Log - Buy-Out |  |  | X
PM 2 | Subcontract SOW | Sign-Off | Review | X
PM 2 | Subcontractor Contract | Sign-Off | Review | X
PM 2 | Subcontractor OCIP Negotiation | Sign-Off | Review | X
PM 2 | Sub Reccomendation of Award | Sign-Off | Review | X
PM 2 | Allocation & Allowance Design Verification |  |  | X | Support
PM 2 | Allocation & Allowance Subcontract Pricing | Sign-Off | Review | X
PM 2 | Allocation & Allowance Subcontract Award or CO | Sign-Off | Review | X
PM 2 | Manage OAC Meeting (Minutes, Follow-Thru, Meeting) |  |  | X
PM 2 | Design Center Build-Out |  |  | X |  | Support
PM 2 | PM Building Envelope, Exterior Finishes, Interior Finishes Subcontractors |  |  | X |  | Support
PM 1 | Write, Send, Follow-Up, Distribute RFI's |  |  |  | X | Support
PM 1 | Add Change Events for Cost RFI's not in Bulletin/Dwg Rev |  |  |  | X
PM 1 | Review, Submit, Distribute Submittals |  |  |  | X | Support
PM 1 | Manage BIM Process, Schedule, Deliverables |  |  |  | X | Support
PM 1 | Verify Coordination in Field Being Implemented Weekly |  |  |  | X
PM 1 | Update RFI Log Weekly |  |  |  | X | Support
PM 1 | Update Submittal Log Weekly |  |  |  | X | Support
PM 1 | Provide Full Submittal Requirements Log per Contract/Dwg/Spec |  |  |  | X
PM 1 | Update 12 Week Look-Ahead Schedule - Submittals & Procurement Sections |  |  |  | X
PM1 | Update Procurement Log Monthly (Checked to Schedule Update) |  |  | Support | X | Support
PM1 | PM Structural, Framing, Drywall, MEP, Utilities, Life Safety |  |  |  | X | Support
PA | Write, Send, Follow-Up, Distribute RFI's |  |  | Support | Support | X
PA | Update Procurement Log Monthly (Checked to Schedule Update) |  |  | Support | Support | X
PA | Solicit, Review, Submit, Distribute Submittals |  |  | Support | Support | X
PA | Assemble Weekly Safety Audits into Monthly Safety Audit Rpt |  |  |  |  | X
PA | Print & File RFI's in Field Binder for RP to Post to Drawings (Every 2 weeks) |  |  |  |  | X
PA | Manage all Permitting w/ County, Town, Site Agencies, Bullletins, Sub Permits (Weekly) |  |  | Support | Support | X
PA | Improve & Maintain Permit Log (Monthly); Maintain Field Hardcopies/Binder |  |  |  |  | X
PA | Manage Drawing Sets in Procore (As received) |  |  |  | Support | X
PA | Overlay Drawing Sets in Procore, Do Dwg Check For Initial Scope Changes |  | Support |  |  | X
PA | Distribute Drawings to Subs w/ SPM Worded Pricing Deadline Paragraph |  | Support |  | Support | X
PA | Get from Subs Monthly & Maintain As-Built Drawings |  |  |  | Support | X
PA | Get Field, 24x36" Hardcopy Drawing Update Sets (ei Master Permit, Bull 4) |  |  |  | Support | X
PA | Manage Sub Field Paperwork is Compliant (Dalies, 2 WK Look-Aheads, Toolbox..) |  |  |  |  | X
PA | Maintain SWPPP & Dewatering Log Binders / Reporting |  |  |  |  | X
PA | Maintain and Update During Meeting OAC Minutes |  |  | Support |  | X
PA | Input Subs into OCIP Portal for Enrollment |  |  |  |  | X |  | Support
PA | Maintain and Update During Meeting Sub Minutes |  |  |  | Support | X
QAQC | Design Doc Coordination (Draft RFI's, Review Submittals, Track Dwg/Spec Req Rev's) |  | Support | Support | Support |  | X
QAQC | Field Verification of Critical QAQC Items | [5 empty] | X
QAQC | Threshold Inspection Coordination |  |  |  |  | Support | X
QAQC | Manage Waterproofing Consultant Inspection & Report Closeout Documentation | [5 empty] | X
QAQC | Quality Built Inspection Coordination & Report Closeout Documentation | [5 empty] | X
Proj Acct | Process Sub Payment Applications & Invoices |  | Support |  |  |  |  | X
Proj Acct | Prepare Pencil Copy Payment Application |  | Support |  |  |  |  | X
Proj Acct | Prepare Final Payment Application |  | Support |  |  |  |  | X
Proj Acct | Send Final HB Signed Pay App to Owners |  | Support |  |  |  |  | X
Proj Acct | Verify P&P Bonds Received & Valid; Provide Bond Acct Monthly Report |  | Support |  |  |  |  | X
Proj Acct | Receive all Releases Monthly | [6 empty] | X
Proj Acct | Verify Weekly Payroll Report Accurate | [6 empty] | X
Proj Acct | Verify Subcontractor Award Checklist Complete prior to Procure 'Approval' Status |  | Support | Support |  | Support |  | X
Proj Acct | Request and Maintain COI (GL,Auto, WC, Umbrella, Stored Mat, Add Ins HB/JDL's) |  |  |  |  | Support |  | X
Proj Acct | Sync Project COI w/ Procore COI & Main Office Status | [6 empty] | X
Proj Acct | Verify Procore Project Insurance Report Updated Monthly, PDF Sent to MWC |  |  |  |  | Support |  | X
PM's | Monday by 12 PM - Have all weekly reports updated for OAC Agenda
All | Friday's - Get Payroll Time into HH2 (you verify your time is in, not rely on Tacara)
All | Weekly - Get Personal Expense Reports in
PM's/Supers | 5th, Vehicle Reimbursement Due
PM/Super | 7th, Get BOA or Speedway Concur Reports submitted
SPM | 14th, Financial Reports finalized in folder
SPM | 15th, Change Orders submitted to Owner
Proj Acct | 24th, Pencil Copy Pay App Due
All | 25th, Get Personal Expense Reports in no later than
Proj Acct | 3rd, Final Pay App Sent by end of month 28th-31st
PM's | 5th, Financial (& Non Financial) Reports Due

## Field
[DATE] | RESPONSIBILITY MATRIX for [PROJECT]
|  | [Name] | [Name] | [Name] | [Name] | [Name]
Task Category | Tasks/Roles | Lead Super | MEP Super | Interior Super | Asst Super | QaQc
Lead Super | Overall Job Lead | X
Lead Super | Monthly Schedule Updates | X | Support | Support | Support
Lead Super | 3 week look Aheads | X | Support | Support | Support
Lead Super | Review Sub Pay Apps | X | Support | Support | Support
Lead Super | Site Work | X
Lead Super | Landscape | X
Lead Super | Hardscape | X
Lead Super | Utilities | X
Lead Super | Courtyard | X
Lead Super | Road Work | X
MEP Super | MEP for Units, Amentities , Exteriors, And Courtyard |  | X
MEP Super | Interiors of Units until Drywall has been Hung |  | X
MEP Super | Interior's for all trades Amenities until completion |  | X
MEP Super | Exterior Lighting |  | X
MEP Super | Site Logistics |  | X
MEP Super
MEP Super
MEP Super
Interior/ Envelope | Exterior Envelope Stucco, Roof, Windows, Exterior Facades, and Painting |  |  | X | Support
Interior/ Envelope | Interiors Once drywall has been hung |  |  | X | Support
Interior/ Envelope | Flooring Sub |  |  | X | Support
Interior/ Envelope | Painting sub |  |  | X | Support
Interior/ Envelope | MEP Trim Out |  |  | X | Support
Interior/ Envelope
Interior/ Envelope
Interior/ Envelope
Interior/ Envelope
Interior/ Envelope
Interior/ Envelope | Exterior Envelope Stucco, Roof, Windows, Exterior Facades, and Painting |  |  | Support | X
Interior/ Envelope | Interiors Once drywall has been hung |  |  | Support | X
Interior/ Envelope | Resi Cabinets Sub |  |  | Support | X
Interior/ Envelope | Wood Trim and Doors Sub |  |  | Support | X
Interior/ Envelope | Window Covering Sub |  |  | Support | X
Interior/ Envelope | MEP Trim Out |  |  | Support | X
Interior/ Envelope
Interior/ Envelope
Interior/ Envelope
Interior/ Envelope
Interior/ Envelope
Interior/ Envelope
Interior/ Envelope
Interior/ Envelope
Interior/ Envelope
Interior/ Envelope
QAQC | Review all building envelop Submittals and Details | Support | Support | Support | Support | X
QAQC |  | Support | Support | Support | Support | X
QAQC |  | Support | Support | Support | Support | X
QAQC
QAQC
QAQC
QAQC
Shared Dates/ Reminder
It is all Supers Responsibility to review all Submittals and Shops
Supers need to provide QA QC with List of items that need to be reviewed Minimum 60 days before