PROJECT MANAGEMENT PLAN

PROJECT NAME

JOB NO. 00-000-00

Submitted by:							Approved By:

Project Manager						Project Executive

Project Team Signatures:

Distribution:

Residential	 Commercial

Joe Morin, President Luxury Residential	Arthur Miller, Vice President Commercial

Assigned PX Name, Project Executive	Assinged PX Name, Project Executive

Project Team Assignment:

Project Executive

Safety Manager

QA/QC Manager

I.  Project Team Philosophy:

We believe in strategic planning and in the project team assignment for each project that we undertake.  We also believe in providing clear lines of responsibility and accountability for achieving the goal of successfully completing our projects and exceeding the expectations of our clients.  Bringing Visions to Reality is not limited to just the project team assigned to this project, but it involves our entire staff.

Our commitment is to dedicate the involvement of the team assigned to this project and to ensure that the Owner and Architect will receive the personal attention essential to the success of this project.  Our prime concern is and will continue to be a company-wide commitment of integrity and service, thus providing quality construction on time and within budget.

This Project Management Plan shall be implemented through the lens of GRIT in every decision.

GROWTH: I will wake up every day hungry for improvement, knowing that I can do better and that, as a team, we can do better. I will do what it takes to achieve both personal and company goals.

RESOURCEFULNESS: I will look for problems and deliver solutions, including asking for God's wisdom. I will strive daily to enhance my expertise and ensure quality in everything I do.

INTEGRITY: I will always speak the truth and listen carefully to all perspectives before taking action. I will honor my commitments and consistently do what is right, fostering trust and accountability.

TEAM: I will set aside my ego for the greater good of our team. I will fully commit and be 'all in' to execute the company's priorities.

II.  Quality Control:

- The Project Team will complete the project, exceeding the Owner and Hedrick Brothers’ Standard of Quality.

- The Project Team will communicate to the Owner, Architect, and Consultants their primary quality considerations for the project.

- The Project Manager and Project Superintendent will pre-qualify all subcontractors and will demand quality, service, and dedication throughout the project’s duration.

  - Pre-qualification is a collaborative process: a list of potential subcontractors is compiled and provided to our Risk Management team, who then registers these companies in Compass, our dedicated pre-qualification platform. The Risk Management team leads this effort, with support from the operations team—including the Project Manager and Superintendent—after the project transitions from Preconstruction to Operations.

- The Project Manager will hold independent team meetings to discuss schedules, procurement, pre-installation needs, safety, staffing and budget.

- The Project Manager, Project Superintendent, and Project Executive will note and discuss areas of special concern as indicated:

- The Project Superintendent oversees all aspects of work quality on the job site and manages a detailed three-week look-ahead schedule along with the overall construction tracking schedule with support from the Project Manager.

- The Project Superintendent ensures all trades perform work, as defined by their respective Scope of Work, in compliance with the Contract Documents.

- The Project Manager and Project Superintendent shall coordinate field mock-ups and samples for approval by the Architect, Owner, and/or Hedrick Brothers Quality Control Manager.

- The Project Superintendent will maintain a rolling punch list of all outstanding quality and detail issues using the Procore Observations tool. This ongoing punch list will be distributed to each affected subcontractor in the method(s) deemed most effective by the Project Team (e.g. directly from Procore, email, etc.). Subcontractors are expected to resolve listed items within one week of the posting date. Hedrick Brothers aims to have zero punch-list items remaining at Substantial Completion for every project. The Project Manager and Lead Superintendent shall complete the Project Closeout Guide, Pre-Certificate of Occupancy and Closeout Checklist, and the Completion and Acceptance Manual.  These are to be reviewed with, and acknowledged by, the Project Team.

- The Project Manager will collaborate with the Superintendent to review and initiate a Hedrick Brothers completion list (pre-punch) in accordance with the project schedule. Completion lists will be distributed to each affected subcontractor using the most effective communication methods and displayed in each relevant area for sign-off upon the completion of each item. Project teams should utilize the Procore Observations tool and its workflow which allows for digital and collaborative issue resolution. Subcontractors are expected to complete all items within one week of the posting date. Once Hedrick Brothers confirms that the punch list has been satisfactorily completed, the Architect and Owner will be invited to issue their respective punch list which will be formally documented in the Procore Punch List tool by the Hedrick Brothers Project Team. This subsequent list will be posted in the same manner, with each trade required to complete and sign off on their items within one week.

  - Punch List Manager for this Project:________________________

III. Preconstruction Meeting:

- The Project Manager and Project Superintendent will coordinate and conduct a Preconstruction Conference at the job site (or via approved virtual/hybrid format if necessary) with the Owner or Owner’s Representative, the Architect/Engineer, all major subcontractors, and other key stakeholders. Formal notices, including a detailed agenda, will be distributed to all required attendees at least seven (7) calendar days in advance of the meeting. An attendance sign-in sheet will be maintained, and formal minutes documenting discussions, decisions, and action items will be prepared and distributed, via the Procore Meetings tool, by the Project Manager within three (3) business days following the meeting.

- The Superintendent will review the Site Plan/Staging Plan with all subcontractors to ensure a shared understanding of parking arrangements, material deliveries and unloading zones, material storage locations, temporary utilities, site access/egress points, erosion/sediment control measures, and other site-sensitive issues, including the Owner’s specific requests or restrictions.

- All attendees will receive introductions, including full contact information and a clear delineation of roles, responsibilities, and decision-making authority for each party (e.g., Project Manager for budget and schedule matters, Superintendent for daily field operations, Architect for design interpretations, etc.).

- The contract documents, including scope of work, specifications, drawings, and any addenda, will be reviewed to confirm boundaries, exclusions, and interdependencies among trades.

- The approved project schedule, including baseline critical path activities, key milestones, long-lead item procurement, and update procedures, will be presented and discussed, with confirmation of each party’s understanding of sequencing and dependencies.

- Communication protocols will be established, including processes and timelines for Requests for Information (RFIs), submittals, shop drawings, and correspondence, as well as schedules for progress meetings, safety briefings, mockups/box walks, and issue escalation.

- Project safety requirements will be reviewed in detail, including the Contractor’s site-specific safety plan, OSHA compliance, hazard identification, personal protective equipment mandates, incident reporting procedures, and the authority to halt unsafe work.

- Quality control and assurance procedures will be outlined, including inspection requirements (internal, third-party, and jurisdictional), testing protocols, corrective action processes for non-conforming work, and documentation standards.

- Administrative and financial procedures will be confirmed, encompassing payment application requirements and schedules, change order identification/approval processes (including documentation and pricing rules), retainage terms, lien waiver protocols, and preliminary closeout requirements (e.g., as-built drawings, warranties, and punch-list resolution).

- Any remaining permits, insurance certificates, bonds, or regulatory compliance items will be verified as current and on file.

IV.  Safety:

- Write project specific safety plan (note-book) required by OSHA.

- Conduct regular safety inspections.

- Report all accidents, near misses, and violations.

- Write citations to all Hedrick Brothers employees and subcontractors in violation of safety rules.

- Maintain SDS sheets in 3-ring binder as well as copies of reports and violations.

- The Superintendent shall support the Safety Department 100%.

- The Superintendent and/or Safety Coordinator shall exercise their authority to request any safety violators leave the job site at any time.

  - The Project Safety Officer will be  Assigned Hedrick Brothers Safety Coordinator .  Their duties shall be:

  - All HB personnel will be trained and certified in First Aid & CPR.

  - The Project Superintendent will enforce Hedrick Brothers safety rules on the job site:

  - Hard hats	§	Shirts (Non offensive)	§	Fall Protection

  - Work Boots	§	No radios/ headphones	§	Work Gloves

  - Long pants	§	Safety glasses	§	Respirators

    - All temporary power will be GFI protected.

    - All scaffolding is to be OSHA compliant and tagged.

    - Alcohol and controlled substance use will not be permitted nor tolerated on the job site.

    - The Project Superintendent will conduct a site-specific safety orientation for each subcontractor prior to their commencement of work on the job site. Safety orientations are an ongoing effort; all new personnel shall attend and acknowledge their understanding of the instruction prior to commencing work on the job site regardless of when they join the project team.

    - Violators of any safety rules will receive no grace period for loss of work.  All subcontractors are required to maintain their schedule at their own expense.

    - Accident reports are to be filled out in accordance with Hedrick Brothers Procedures.

    - The Project Manager, Project Superintendent, or both will notify the Hedrick Brothers Principle In-Charge of any Crisis immediately. Crisis Communication Plan linked here.

    - The Project Manager and Project Superintendent are to implement hurricane procedures as written in the Tropical Storm/Hurricane Preparedness Plan.

- The Project Manager, Project Superintendent, and the Safety Officer are responsible for achieving the following safety goals:

- Maintain an accident-free job site.

- Receive no written citations from Project Safety Officer.

- Daily Subcontractor and vendor Sign-in.

- Have no OSHA violations or fines.

- The Project Superintendent is responsible for keeping the job site clean from trash, construction debris, and hazardous materials daily.  If any subcontractor does not maintain their own cleanup responsibilities to the satisfaction of Hedrick Brothers, Hedrick Brothers will provide the labor and back charge the subcontractor $0.00 per man hour.

  - Safety Concerns to be addressed:

V.  Maintaining Cost Control:

- This contract is based on a  contract in the amount of $ 0.00 			.

- Areas of potential buy out are:

  - Areas of potential risks are:

  - Areas of potential savings are:

- The Project Manager is responsible for reviewing the Job Cost History Report and budget monthly. They will review all budget items related to Superintendents with the Lead Superintendent monthly.

- The Project Superintendent shall review credit card expenses with the Project Manager on a weekly basis.

- All Project Team members who have been issued a gas card or credit card by Hedrick Brothers Construction are responsible for submitting expense reports for review and approval by the Project Executive in accordance with the current policies and procedures.

- The Project Manager will email the Shared Services teams which cost codes they are able to use when billing against this project.

- The Project Manager is responsible requesting the setup of approval routing rules in TimberScan, for completing the review and approval of all invoices (properly cost coded in TimberScan) and subcontractor pay applications (Procore) by the 20th of each month so that the Accounting/Project Team can complete Owner billing by the 25th.

- The Project Executive is to review all timecards for the project and approve the hours of each Project Team member in HH2 no later than close of business on Tuesday morning of each week.

- The Project Manager is responsible for all spending related to the project.  Miscellaneous spending is to be approved and authorized by the PM.

- The Project Manager and Superintendent are to discuss and agree on potential overtime.  Authorization by the Project Manager is required before any overtime will be paid for non-salaried employees.

- The Project Superintendent is responsible for obtaining signed field directives or verification of change order approval from the Project Manager prior to commencement of work that deviates from the Contract Documents.

VI.  Project Schedule:

- The Project start date is      . Project Substantial Completion Date, per contract, is      . The contract states that overall duration of this project from Notice to Proceed / Building Permit / Contract Execution to substantial completion is 0 Calendar / Business / Week days.

- Notice to Proceed was issued to Hedrick Brothers on      .  Notice of Commencement was recorded on       and expires on      .

- The Project Team’s goal is to reach Substantial Completion by       and Final Completion by      .

- The Project Manager and Project Superintendent are required to complete the project as stipulated in the contract.  Liquidated Damages are  applicable at $ 0.00 per .

- The Project Manager will update the project schedule       per the Project Manager and the Project Superintendent.

- The Project Superintendent will keep an original contract schedule and a current lookahead schedule posted in the job site trailer.

- The Project Manager and Project Superintendent have identified the following Critical Path concerns:

VII. Project Team Members Responsibilities:

- All responsibility assignments that follow are to be further defined and clarified in the Responsibility Matrix which is to be completed by the project team prior to mobilization and after any changes to the project staffing. Job Descriptions can be found in BambooHR in the Files section. Examples of typical responsibilities are listed below:

- The Project Executive is to stay updated on the project progress, schedule, budget and to provide support to the Project Team.

- The Project Manager is summarily responsible for, but not limited to, the following:

- Overall management of the project and personnel.

- Communication with the Owner and Architect, at a minimum, on a weekly basis.  This is imperative for maintaining successful working relationships.

- Award and issue subcontracts no later than       (60 days post-mobilization), following the Subcontractor Buyout Process.

- Schedule Pre-Construction Meeting and Weekly Job Site Meetings.

- Draft, issue, track, and distribute Requests For Information (RFI’s).

- Cost Code all Invoices and approve timecards.

- Resolve conflicts both with the Project Team and field related issues.

- Be available to the Architect, Owner, and Project Superintendent at all times.

- Review and approve Pay Request.

- Submit Pay Request to Owner/Architect and resolve any conflicts to ensure timely payment.

- Review Budget with Project Team monthly.

- Prepare, maintain, and submit a monthly financial forecasting report reflecting current project cost, revenue, cash flow, risk, etc. as required by the current SOP.

- Prepare and submit weekly reports/ update to the Project Executive prior to the weekly Ops Meeting.

- Maintain Schedule in accordance with the current SOP.

- Review and approve shop drawings and submittals.

- Validate, negotiate, and process Change Orders with the Owner, Architect, and Subcontractors, ensuring alignment with contract terms, scope, schedule, and budget.

- The Assistant Project Manager or Project Administrator is responsible for, but not limited to:

- Prepare all meeting minutes and submit them to Project Manager for review and distribution following approval.

- Process shop drawings, submittals, and RFI’s.

- Maintaining RFI log

- Maintaining Submittal log.

- Maintaining drawings, specifications & revisions.

- Meeting agendas and minutes.

- Maintain Buyout Log with guidance from the Project Manager.

- Distribute and file all project correspondence and documents.

- Contribute to the project schedule maintenance and distribute formalized updates.

- Collect and prepare close-out documents including maintenance manuals, guarantees, warranties, as-builts, etc.

- Prepare and complete documentation for completion of punch list.

    - The Project Superintendent is responsible for, but not limited to:

- Coordinate all subcontractor field activity and supplier deliveries to the job site.

- Schedule all inspections.

- Keep track of as-built drawing status.

- Responsible for all activities on the job site including safety and quality of craftsmanship.

- Fill out, close, and distribute the Daily Construction Reports in Procore.

- Fill out and submit timecards through HH2.

- Conduct weekly subcontractor meetings on site, capturing the agenda and minutes in Procore.

- Review RFI’s and project schedule with Project manager.

- Schedule all on site testing to be performed.

- Maintain a clean site free from debris and hazardous materials.

- Verify all subcontractor layouts.

- Review subcontractor pay applications with the Project Manager.

- Verify all materials delivered to the project are in accordance with plans, specifications, and approved submittals.

- Review first work of all activities to ensure strict quality control.

- Maintain and update field look-ahead schedule (3-week or 4-week) and distribute to subcontractors weekly.

- Maintain a safe site and OSHA compliance.

        - The Project Accountant is responsible for, but limited to:

- Track subcontracts.

- Prepare monthly billing and provide required backup.

- Process all subcontractor and supplier billing.

- Log and track Notices to Owner.

- Request and track all lien waivers.

- Process all miscellaneous billings.

- Review and approve cash requirements for Project Manager final approval.

- Process and distribute weekly job cost reports.

- Update changes in the budget as needed.

- The Project Team will review the Project Management Plan monthly and maintain strict accountability to the Project and Hedrick Brothers Construction.

VIII.  Project Site Management:

- Superintendent’s Project Plan: The Project Superintendent will develop and maintain the overall approach to managing the construction site as follows:

Safety

Utility and Service Issues

Traffic and Pedestrian Considerations

Site Security and Visitor Check-in

Dust Control & Erosion

Noise Control and Working Hours

Site Maintenance

Existing Site Conditions

Permits

Site Work Issues & Concerns

IX. Project Administration:

- The Project Team shall maintain a good working relationship and maintain a positive relationship with the Owner, Architect, Consultants, Building Officials and subcontractors.

- The Project Team shall develop a good working relationship with the Building Department and always provide them with required documentation.

- The Project Team will be proactive in documenting and resolving potential disputes or problems at the earliest indication.

X.  Project Closeout:

- The Project Manager and   are to submit Project Closeout Manual at the Final Completion Meeting.

- The Project Manager is to schedule Facilities Operations meeting for the Owner.

- The Project Manager and Project Superintendent are responsible for collecting and reviewing all as-built drawings to be submitted 30 days prior to Substantial Completion.

- The Project Superintendent is to have the Punch List 100% complete       days before Final Completion and have sign-off by Owner/Architect.

- The project paperwork is to be finalized, closeout complete, and filed by      .

- The Project Team is to have a final review of the project and budget.

- The Project Team will meet Hedrick Brothers Executives and summarize the project, project costs, subcontractor performance, and lessons learned.

XI. Attachments to Be Included:

01 	Project Management	02	Project Administration

Estimate		Responsibility Matrix

Qualifications		List of Who to Contact

Phasing Plan (if applicable)		Meeting Agenda Templates (in Procore)

Logistics Plan		Pay App Procedures (Subcontractor & Owner)

Construction Schedule		Hurricane & Tropical Storm Preparedness Plan

Project Budget (from Procore Budget)		Crisis Management & Ice Response Plans

Schedule of Values		Lessons Learned Report (coming soon)

IDS Requirements (coming soon)		Subcontractor Scorecards (coming soon)

Startup Checklist with Assignment (Procore Inspections)

Submittal Register	03	Quality & Safety

Closeout Procedure Guide (coming soon)		Safety – Project Startup Process

Completion & Acceptance Manual (coming soon)		Project Specific Safety Plan

Closeout & Pre-CO Checklist (Procore Inspections)		Quality Control Program