## ActionItems
Purpose of the Constraints Log The Constraints Log is a structured tool designed to systematically track issues that may affect the progress or cost of a construction project. It organizes these issues into predefined categories, such as 1. Permits, 2. AHJ Coordination, 3. Design Development, 4. Utility Service Providers, 5. Hedrick Brothers Internal Coordination Items, 6. Construction Progress, and 7. {New Section}. Each standard category (1 through 7) is divided into "OPEN" and "CLOSED" subcategories to distinguish active issues from resolved ones. Additionally, the log includes two specialized sections—Change Tracking and Delay Log—with distinct column arrangements for monitoring project changes and delays. Adding and Managing Entries Creating New Entries Insert new issues into the appropriate “OPEN” subcategory within the relevant category. Utilize the predefined numbering system (e.g., 1.01, 2.01) to ensure consistency. The “No #” values are fixed record identifiers and should not be modified unless strictly necessary. Closing Entries Upon full resolution of an issue, cut the entire row from its current position in the “OPEN” subcategory and paste it into the corresponding “CLOSED” subcategory below. Update the “Completion Date” column with the resolution date. This action will cause the “Days Elapsed” value to recalculate automatically as the difference between the Completion Date and Date Identified. Inserting Additional Rows Each section contains hidden rows at the end to accommodate future entries. To add more rows within an existing section, unhide the rows at the bottom of that section (typically grouped and hidden via Excel’s row grouping or hide feature), then populate as needed. Adding New Sections To create an additional category, copy the entire block of rows for the template section titled “7. {NEW SECTION} - OPEN” (rows 628 through 727 in the current template structure, including the associated “CLOSED” placeholder rows and blank spacing). Paste this block immediately above the “Change Tracking” section (currently beginning around row 731). After pasting, update the section numbering by modifying the first item’s “No #” value (e.g., change “7.01” to “8.01”). The subsequent items in the new section (e.g., 7.02, 7.03) will automatically adjust to match the new section prefix (e.g., 8.02, 8.03) due to the relative numbering format used in the template. | [6 empty] | Column Descriptions The standard sections utilize the following columns: - No #: Text-based record identifier (predefined; modify only if necessary). - Description: Text providing a brief title or summary of the issue. - Date Identified: Short date indicating when the issue was first recognized. - Status: List selection denoting the current state (e.g., Identified, In Progress). - Days Elapsed: Numeric value, calculated as the days between the current system date and "Date Identified" for open items, or between "Completion Date" and "Date Identified" for closed items (leave blank for unused rows). - Reference: Text for referencing related documents, events, or sources. - Responsible: Text specifying the company accountable for the issue. - B.I.C.: Text identifying the individual or entity currently responsible for advancing the item. - Due: Date representing the required closure deadline. - Completion Date: Date recording when the issue was fully resolved. - Comments: Text for supplementary notes, explanations, or updates. Specialized Sections - Change Tracking: Tracks potential or approved changes, with columns including CE #, CE Description, Date Identified, Status, Reason, Origin, CO Total, CO Date, CO Status, Schedule Impact (Days), and Comments. - Delay Log: Monitors delays, with columns such as No #, Description, Date Identified, Status, Owner Notified, Affected Activity, CP Impact (Y/N), Exp/Actual Duration (Days), Delay Start, Potential Cost Impact, and Comments. Maintenance Guidelines Update the log at least weekly to ensure accuracy and timeliness. Review all open items during project meetings, assign responsibilities as needed, and verify calculations (e.g., Days Elapsed) for integrity. This practice supports proactive issue resolution and informed decision-making throughout the project lifecycle. If questions arise regarding usage, consult the project lead for clarification.
{Project Name} Constraints Log
DUE IN 8 DAYS+
LAST UPDATED: | 2023-06-27 | [6 empty] | DUE IN NEXT 7 DAYS
DATE PAST DUE
No # | DESCRIPTION | DATE IDENTIFIED | STATUS | DAYS ELAPSED | REFERENCE | RESPONSIBLE | B.I.C | DUE | COMPLETION DATE | COMMENTS
1. PERMITS - OPEN
1.01
1.02
1.03
1.04
1.05
1.06
1.07
1.08
1.09
1.1
1.11
1.12
1.13
1.14
1.15
1.16
1.17
1.18
1.19
1.2
1.21
1.22
1.23
1.24
1.25
1.26
1.27
1.28
1.29
1.3
1.31
1.32
1.33
1.34
1.35
1.36
1.37
1.38
1.39
1.4
1.41
1.42
1.43
1.44
1.45
1.46
1.47
1.48
1.49
1.5
1.51
1.52
1.53
1.54
1.55
1.56
1.57
1.58
1.59
1.6
1.61
1.62
1.63
1.64
1.65
1.66
1.67
1.68
1.69
1.7
1.71
1.72
1.73
1.74
1.75
1.76
1.77
1.78
1.79
1.8
1.81
1.82
1.83
1.84
1.85
1.86
1.87
1.88
1.89
1.9
1.91
1.92
1.93
1.94
1.95
1.96
1.97
1.98
1.99
1. PERMITS - CLOSED
2. AHJ COORDINATION - OPEN
2.01 | Right Turn Lane North Approach | 2021-12-14 | IN PROGRESS | 1114 | PBC Comments - Monitoring ENG-003b | WGI | AGC | 2023-06-16 |  | Work underway as of 05/19/2023, Asphalt completion target 06/29/2023 07/18/2023
2.02 | Median Landscaping at Jog Road | 2021-12-14 | IN PROGRESS | 1114 | PBC Comments - Monitoring ENG-006b | WGI | AGC | 2023-06-23 |  | Final inspection to occur following completion of NB turn lane extension (expected by end of June 2023)
2.03 | Jog Road South Approach Left Turn Lane Extension | 2021-12-14 | IDENTIFIED | 1114 | PBC Comments - Monitoring ENG-008B | WGI | AGC | 2023-06-16 |  | Work to begin in conjunction with SB deceleration lane (item 2.01)
2.04 | Amenity Completion | 2021-12-14 | IN PROGRESS | 1114 | PBC Comments - Monitoring PARKS-001 | WGI | AGC | 2023-04-14 |  | Currently tracking for on-time completion prior to 1st TCO application
2.05
2.06 | AHJ CLOSE-OUT REQUIREMENTS | 2023-04-18 |  | 764 | Close-Out Tracking Log (LINK) | AGC & ADC | AGC |  |  | Close-Out requirement tracking log linked in column 'E' of this log item for ease of access
2.07
2.08
2.09
2.1
2.11
2.12
2.13
2.14
2.15
2.16
2.17
2.18
2.19
2.2
2.21
2.22
2.23
2.24
2.25
2.26
2.27
2.28
2.29
2.3
2.31
2.32
2.33
2.34
2.35
2.36
2.37
2.38
2.39
2.4
2.41
2.42
2.43
2.44
2.45
2.46
2.47
2.48
2.49
2.5
2.51
2.52
2.53
2.54
2.55
2.56
2.57
2.58
2.59
2.6
2.61
2.62
2.63
2.64
2.65
2.66
2.67
2.68
2.69
2.7
2.71
2.72
2.73
2.74
2.75
2.76
2.77
2.78
2.79
2.8
2.81
2.82
2.83
2.84
2.85
2.86
2.87
2.88
2.89
2.9
2.91
2.92
2.93
2.94
2.95
2.96
2.97
2.98
2.99
2. AHJ COORDINATION - CLOSED
2.05 | School Bus Shelter Completion | 2021-12-28 | CLOSED | 381 | PBC Comments - Monitoring SCHOOL-002 | WGI | AGC | 2023-04-14 | 2023-06-13 | Slab accessibility resolution provided to ADC and implemented in field, TPO complete, pending Stucco
3. DESIGN DEVELOPMENT
3.01
3.02
3.03
3.04
3.05
3.06
3.07
3.08
3.09
3.1
3.11
3.12
3.13
3.14
3.15
3.16
3.17
3.18
3.19
3.2
3.21
3.22
3.23
3.24
3.25
3.26
3.27
3.28
3.29
3.3
3.31
3.32
3.33
3.34
3.35
3.36
3.37
3.38
3.39
3.4
3.41
3.42
3.43
3.44
3.45
3.46
3.47
3.48
3.49
3.5
3.51
3.52
3.53
3.54
3.55
3.56
3.57
3.58
3.59
3.6
3.61
3.62
3.63
3.64
3.65
3.66
3.67
3.68
3.69
3.7
3.71
3.72
3.73
3.74
3.75
3.76
3.77
3.78
3.79
3.8
3.81
3.82
3.83
3.84
3.85
3.86
3.87
3.88
3.89
3.9
3.91
3.92
3.93
3.94
3.95
3.96
3.97
3.98
3.99
3. DESIGN DEVELOPMENT - CLOSED
4. UTILITY SERVICE PROVIDERS - OPEN
4.01
4.02
4.03
4.04
4.05
4.06
4.07
4.08
4.09
4.1
4.11
4.12
4.13
4.14
4.15
4.16
4.17
4.18
4.19
4.2
4.21
4.22
4.23
4.24
4.25
4.26
4.27
4.28
4.29
4.3
4.31
4.32
4.33
4.34
4.35
4.36
4.37
4.38
4.39
4.4
4.41
4.42
4.43
4.44
4.45
4.46
4.47
4.48
4.49
4.5
4.51
4.52
4.53
4.54
4.55
4.56
4.57
4.58
4.59
4.6
4.61
4.62
4.63
4.64
4.65
4.66
4.67
4.68
4.69
4.7
4.71
4.72
4.73
4.74
4.75
4.76
4.77
4.78
4.79
4.8
4.81
4.82
4.83
4.84
4.85
4.86
4.87
4.88
4.89
4.9
4.91
4.92
4.93
4.94
4.95
4.96
4.97
4.98
4.99
4. UTILITY SERVICE PROVIDERS - CLOSED
5. HEDRICK BROTHERS INTERNAL COORDINATION ITEMS
5.01
5.02
5.03
5.04
5.05
5.06
5.07
5.08
5.09
5.1
5.11
5.12
5.13
5.14
5.15
5.16
5.17
5.18
5.19
5.2
5.21
5.22
5.23
5.24
5.25
5.26
5.27
5.28
5.29
5.3
5.31
5.32
5.33
5.34
5.35
5.36
5.37
5.38
5.39
5.4
5.41
5.42
5.43
5.44
5.45
5.46
5.47
5.48
5.49
5.5
5.51
5.52
5.53
5.54
5.55
5.56
5.57
5.58
5.59
5.6
5.61
5.62
5.63
5.64
5.65
5.66
5.67
5.68
5.69
5.7
5.71
5.72
5.73
5.74
5.75
5.76
5.77
5.78
5.79
5.8
5.81
5.82
5.83
5.84
5.85
5.86
5.87
5.88
5.89
5.9
5.91
5.92
5.93
5.94
5.95
5.96
5.97
5.98
5.99
5. HEDRICK BROTHERS INTERNAL COORDINATION ITEMS - CLOSED
6. CONSTRUCTION PROGRESS - OPEN
6.01
6.02
6.03
6.04
6.05
6.06
6.07
6.08
6.09
6.1
6.11
6.12
6.13
6.14
6.15
6.16
6.17
6.18
6.19
6.2
6.21
6.22
6.23
6.24
6.25
6.26
6.27
6.28
6.29
6.3
6.31
6.32
6.33
6.34
6.35
6.36
6.37
6.38
6.39
6.4
6.41
6.42
6.43
6.44
6.45
6.46
6.47
6.48
6.49
6.5
6.51
6.52
6.53
6.54
6.55
6.56
6.57
6.58
6.59
6.6
6.61
6.62
6.63
6.64
6.65
6.66
6.67
6.68
6.69
6.7
6.71
6.72
6.73
6.74
6.75
6.76
6.77
6.78
6.79
6.8
6.81
6.82
6.83
6.84
6.85
6.86
6.87
6.88
6.89
6.9
6.91
6.92
6.93
6.94
6.95
6.96
6.97
6.98
6.99
6. CONSTRUCTION PROGRESS - CLOSED
7. {NEW SECTION} - OPEN
7.01
7.02
7.03
7.04
7.05
7.06
7.07
7.08
7.09
7.1
7.11
7.12
7.13
7.14
7.15
7.16
7.17
7.18
7.19
7.2
7.21
7.22
7.23
7.24
7.25
7.26
7.27
7.28
7.29
7.3
7.31
7.32
7.33
7.34
7.35
7.36
7.37
7.38
7.39
7.4
7.41
7.42
7.43
7.44
7.45
7.46
7.47
7.48
7.49
7.5
7.51
7.52
7.53
7.54
7.55
7.56
7.57
7.58
7.59
7.6
7.61
7.62
7.63
7.64
7.65
7.66
7.67
7.68
7.69
7.7
7.71
7.72
7.73
7.74
7.75
7.76
7.77
7.78
7.79
7.8
7.81
7.82
7.83
7.84
7.85
7.86
7.87
7.88
7.89
7.9
7.91
7.92
7.93
7.94
7.95
7.96
7.97
7.98
7.99
7. {NEW SECTION} - OPEN
CHANGE TRACKING
CE # | CE DESCRIPTION | DATE IDENTIFIED | STATUS | REASON | ORIGIN | CO TOTAL | CO DATE | CO STATUS | SCHEDULE IMPACT (DAYS) | COMMENTS
PCCO-001
PCO-15
Delay Log
No # | DESCRIPTION | DATE IDENTIFIED | STATUS | OWNER NOTIFIED | AFFECTED ACTIVITY | CP IMPACT (Y/N) | EXP / ACTUAL DURATION (DAYS) | DELAY START | Potential Cost Impact | COMMENTS
DEL-001 | PBC Permit Delay - PDI Claim | 2023-06-01 | CLOSED W/ EXTENSION | 1900-01-24 |  |  | 4 | 2023-06-22 | 45103
DEL-002
DEL-003
DEL-004
DEL-005
DEL-006
DEL-007
DEL-008
DEL-009
DEL-010
DEL-011
DEL-012
DEL-013
DEL-014
DEL-015
DEL-016
DEL-017
DEL-018
DEL-019
DEL-020
DEL-021
DEL-022
DEL-023
DEL-024
DEL-025
DEL-026
DEL-027
DEL-028
DEL-029
DEL-030
DEL-031
DEL-032
DEL-033
DEL-034
DEL-035
DEL-036
DEL-037
DEL-038
DEL-039
DEL-040
DEL-041
DEL-042
DEL-043
DEL-044
DEL-045
DEL-046
DEL-047
DEL-048
DEL-049
DEL-050
DEL-051
DEL-052
DEL-053
DEL-054
DEL-055
DEL-056
DEL-057
DEL-058
DEL-059
DEL-060
DEL-061
DEL-062
DEL-063
DEL-064
DEL-065
DEL-066
DEL-067
DEL-068
DEL-069
DEL-070
DEL-071
DEL-072
DEL-073
DEL-074
DEL-075
DEL-076
DEL-077
DEL-078
DEL-079
DEL-080
DEL-081
DEL-082
DEL-083
DEL-084
DEL-085
DEL-086
DEL-087
DEL-088
DEL-089
DEL-090
DEL-091
DEL-092
DEL-093
DEL-094
DEL-095
DEL-096
DEL-097
DEL-098
DEL-099
Formulas:
DAYS ELAPSED = IF([DATE IDENTIFIED]="","",IF([COMPLETION DATE]="",NETWORKDAYS([DATE IDENTIFIED],TODAY()),NETWORKDAYS([DATE IDENTIFIED],[COMPLETION DATE])))
DAYS ELAPSED = IF(ISBLANK([COMPLETION DATE]),TODAY()-[DATE IDENTIFIED],[COMPLETION DATE]-[DATE IDENTIFIED])
DUE = WORKDAY([DATE IDENTIFIED],15,0)

## Help (hidden)
HELP |  | © 2017 Vertex42.com
https://www.vertex42.com/ExcelTemplates/action-items-template.html
About
This template provides a simple way to track action items assigned to different members of a group. The template includes two different ways to show priority, using Low/Medium/High or a numeric Rank. You can use them both or delete the column you don't want to use.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
To learn how to add drop-down lists and use conditional formatting to spice up your task lists, see the article listed below.
Add Cool Features to Your To Do Lists
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
Conditional Formatting
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
When you mark the Done column with a check, a conditional formatting rule will change the font in that row to gray.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html